Health and Social Care (Quality and Engagement) (Wales) Act 2020

Digital Health and Care Wales Highlight Report

Reporting Officer: Paul Evans (Duty of Quality), Darren Lloyd (Duty of Candour)

DUTY OF CANDOUR

Overall

| Period Ending | RAG Status | Previous RAG Status |
| --- | --- | --- |
| 28th February 2023 |  |  |

Progress Against Deliverables – Candour

| Theme | Minimum requirement by April 2023 | Baseline @ Dec 2022 | Position @ January 2023 |  | Position @ February 2023 | Position @ March 2023 | Position @ April 2023 | Comments for latest update |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Leadership and culture | Senior responsible leadership in place and driving implementation work |  | 4 |  | 4 |  |  | Executive Medical Director agreed as Executive Lead on Duty of Candour |
|  | Strategic led identified and trained (IM or Non-Exec) |  | 2 |  | 2 |  |  | TBC - Strategic lead will be identified in partnership with DHCW Digital Governance & Safety Committee |
|  | Operational lead identified (executive officer level) |  | 4 |  | 4 |  |  | Associate Director of Information Governance & Patient Safety with day to day management by Serious Clinical Incident Investigation Manager. |
|  | Board awareness training completed |  | 3 |  | 3 |  |  | All nationally developed information, education packages/training will be shared. Internal briefing document being drafted. |
| Governance and accountability structures | Fully developed and signed off Implementation plan for the duty |  | 2 |  | 2 |  |  | This document is being utilised as an implementation plan. |
|  | Implementation of the actions in the implementation plan due to enable duty to be enacted in April. |  | 2 |  | 2 |  |  | All actions listed within this document are either in planning or implementation stages with completion scheduled pre-April 2023 |
|  | Policy-ratified and published |  | 2 |  | 2 |  |  |  |
|  | Any additional SOP’s or policies completed |  | 2 |  | 2 |  |  | Update of the DHCW PTR policy is required. Updated clinical incident investigation policy being drafted to reflect duty of candour requirements. |
| Reporting and information (data to knowledge) | Training needs analysis for reporting requirements for the duty |  | 2 |  | 2 |  |  | Relevant staff undertaking familiarisation with additional section ref duty of candour within capture/incidents module on the OfWCMS Staff receiving specific training on duty of candour from organisation operational lead and DHCWs representative on national duty of candour implementation working group, and member of the duty of candour task & finish group for education & training. |
|  | Candour-related information validation and mechanisms for escalation in place, with plans for review and consideration at appropriate level |  | 2 |  | 2 |  |  | As per current policy and process all incidents are reviewed and actioned daily by the Clinical Informatics Assurance team, any escalation, subsequent review of investigation reports and learning from events is shared with the organisations Incident Review and Learning Group (IRLG) and this group in turn reports to DHCWs Digital Governance & Safety Committee. Incident reports and learning from them is also reported to the Welsh Clinical Informatics Council (WCIC). |
|  | Facilities for primary care providers in place and functionality tested |  | n/a |  | n/a |  |  | This forms part of a work stream being supported by the national stakeholders duty of candour implementation working group but isn’t applicable to DHCW. |
|  | Mechanism and publication schedule / plan in place for Candour Reporting Requirements. |  | 3 |  | 3 |  |  | Utilisation of Duty of Candour section of Incidents report within Capture module within OfWCMS – this will be online for April 2023. The demo version is available for stakeholders to review and familiarise themselves with. |
| Commissioning | A clear and corporately agreed understanding of changes required to incorporate DoC requirements into all commissioning arrangements |  | n/a | n/a |  |  |  | DHCW do not commission services in regards provision of health care therefore this is not applicable. |
| Hosting | A clear and corporately agreed understanding of changes required to incorporate DoC requirements into hosting arrangements |  | n/a | n/a |  |  |  | DHCW do not host services in regards provision of health care therefore this is not applicable. |
| Communication and engagement | All staff are aware of key DoC messages tailored to their organisation |  | 3 |  | 3 |  |  | Task & Finish group from within the national Duty of Candour implementation working group are creating an educational video and information/awareness leaflets for distribution by all NHS bodies to staff – scheduled for release end of February 2023. |
|  | Engagement with workforce and key stakeholders e.g. Service Users |  | 3 |  | 3 |  |  | As Above |
| Training and education | Training Needs analysis for the duty |  | 3 |  | 3 |  |  | Analysis of key staff being undertaken. |
|  | Based on training needs analysis Key and specialist staff training identified and completed |  | 3 |  | 3 |  |  | Task & finish group from within the national Duty of Candour implementation working group are creating an educational video and information/ awareness leaflets for distribution by all NHS bodies to staff – scheduled for release end of February 2023. |

DUTY OF QUALITY

Overall

| Period Ending | RAG Status | Previous RAG Status |
| --- | --- | --- |
| 28th February 2023 |  |  |

Progress Against Deliverables

| Theme | Minimum requirement by April 2023 | Baseline @ Dec 2022 | Position @ January 2023 | Position @ February 2023 | Position @ March 2023 | Position @ April 2023 | Comments for latest update |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Leadership and culture | Senior responsible leadership in place and driving implementation work | 4 | 4 | 4 |  |  | Executive Director of Finance & Business Assurance agreed as Executive Lead on Duty of Quality. Interim Head of Quality Assurance & Regulatory Compliance agreed as Operational Lead. Project plan to implement requirements of Duty of Quality being utilised to map implementation and provide progress reports to DHCW Management Board. |
|  | All staff recognise and understand the organisation’s Quality vision, and their roles within it | 2 | 2 | 3 |  |  | Work is in progress with DHCW Business Change team to provide comms and training to all staff relevant to their roles. First draft ready for review w/c 27/02/2023. |
|  | Commitment, resources and infrastructure in place to implement Duty effectively | 2 | 2 | 2 |  |  | Key workstreams in progress from DoQ Implementation project plan. Further work on this should provide improved score in March. |
| Decision-making | Processes and systems in place to provide demonstrable evidence that Board decisions have been made through Quality lens | 2 | 3 | 3 |  |  | Corporate Governance Manager in process of reviewing Board templates to ensure Six Domains and 5 Enablers are captured. |
| Governance and accountability structures | Board are assured that DoQ is being considered across system | 2 | 2 | 3 |  |  | Corporate Governance Manager in process of updating all reporting templates and BAF to capture requirements for DoQ across all systems and reporting frameworks. |
|  | Routine governance documentation is DoQ-ready | 2 | 3 | 3 |  |  | Corporate Governance Manager in process of reviewing Board templates to ensure Six Domains and 5 Enablers are captured. |
| Reporting and information (data to knowledge) | Mechanism and publication schedule / plan in place for sharing DoQ progress information externally | 2 | 2 | 2 |  |  | Interim HoQ to discuss this action with Corporate Governance and Head of Engagement. |
|  | Quality-related information escalation mechanisms in place, with plans for review and consideration at appropriate level | 2 | 3 | 3 |  |  | Escalation process defined through Quality & Regulatory Group to Management Board via reporting mechanism. ToR in process of update. |
| Commissioning | A clear and corporately agreed understanding of changes required to incorporate DoQ requirements into all commissioning arrangements | 2 | 2 | 2 |  |  | Discussion required to understand how this relates to DHCW activity. |
| Hosting | A clear and corporately agreed understanding of changes required to incorporate DoQ requirements into hosting arrangements | 2 | 2 | 2 |  |  | Discussion required (raised at December Quality Implementation group meeting) on how this relates to National programmes hosted by DHCW. Follow up required at meeting on 31/01/23 |
| Quality Standards | A clear understanding of changes required to existing quality infrastructure and agreed programme of work to align with Quality Standards 2023 | 2 | 2 | 2 |  |  | To be discussed with Corporate Governance Manager, document templates possibly to be updated to reflect quality standards. |
| Quality management system – general | A clear understanding of, and commitment to, a quality management system, with plans in place to identify requirements and current gaps | 2 | 3 | 3 |  |  | Overarching plan to manage duty of quality requirements for DHCW is in use and currently reporting 12% completion after initial 2 weeks, this will be used from to map requirements, including those that arise from the Duty of Quality Implementation Group, and to report progress to DHCW Management Board. |
| Communication and engagement | All staff are aware of key DoQ messages tailored to their organisation | 2 | 2 | 3 |  |  | Work is in progress with DHCW Business Change team to provide comms and training to all staff relevant to their roles. First draft ready for review w/c 27/02/2023. |
| Training and education | At least one member of Board trained, knowledgeable and able to influence Board in relation to DoQ | 3 | 3 | 3 |  |  | Quality & Engagement Act presentation delivered to Board development session in October 2022 by WG, backed up with a Duty of Quality presentation by Head of Quality. Further detailed training will need to be delivered, this will hopefully be supported via the implementation group and WS 5 colleagues and internally at DHCW with support from Business Change Team. |

Achievements

Senior Leadership identified at both Executive and Operational levels

Progress demonstrated on Decision making, Governance, Reporting and QMS Workstreams of Duty of Quality.

DHCW specific Duty of Quality training for all staff in final stages of development

Internal and external governance approach approved by DHCW Management Board

Issues

| Description | Score | Mitigation / Action |
| --- | --- | --- |
| N/A |  | N/A |

Risks – top 3

| Description | Score | Mitigation |
| --- | --- | --- |
| Output from WS 5 on Training in relation to the Duty of Quality | 2 | DHCW will develop an in house solution if a central solution isn’t available |
| N/A |  | N/A |
| N/A |  | N/A |

Tasks for next period

DoQ – Engagement with Directors and/or Heads of Dept to define Quality in their areas, this data will be used to develop first iteration of ‘Always On’ report DoQ – continued engagement with Corporate Governance on relevant workstreams DoQ – Work with Business Change Team to finalise internal training around the duty .

Guidance on Completion

Highlight reports should be very simple presentations of the key achievements, issues and risks. The principle of reporting by exception (only those items outside of plan or expectation) should be used when reporting.

The RAG (red, amber, green) status key below should be used to establish a rating for the reporting period. RAG is not a detailed break down of risk but rather a considered assessment of the likelihood of meeting the objectives in the agreed timeframes.

| RAG Status key |  |
| --- | --- |
| Description | Status |
| Organisation is confident that Deliverable/Key milestone can be delivered |  |
| Organisation has identified that delivery is as risk but manageable OR behind schedule but within tolerance |  |
| Organisation has identified that delivery is at risk with certain aspects having no mitigation or outside of tolerance. |  |
| Organisation has little confidence on delivery AND/OR significantly behind schedule AND/OR critical issue with no mitigation currently available |  |

The scores and colours in the issue and risk tables are not drawn from this key but from the risk register and risk management plan and therefore do not necessarily read across. Top 3 risks and issues with scores should be drawn from your risk register and issues log (see example Risk Management Protocol from NWSSP below).

Progress Against Deliverables – This table details the key deliverables / minimum requirements for the implementation of the Duty of Quality by April 2023. The table should be completed using the key below:

| Stage | Definition |  |
| --- | --- | --- |
| 1 | Exploring and preparing |  |
| 2 | Planning and resourcing |  |
| 3 | Implementing and operationalising |  |
| 4 | Full implementation |  |

Achievements - This should be kept to only those items achieved, tasks complete. Reporting on a latest meeting or draft out to stakeholders is too detailed for a highlight report.

Issues - Issues are those risks that have already happened so in essence the worst that have now come to pass. This will be where the group is directed to focus their energies.

Tasks for next period - Keep this to key definable and achievable tasks. Ie consultation to have begun, training needs analysis to be agreed.