Data Centre Transition

Final Internal Audit Report

April 2022

Digital Health and Care Wales

NWSSP Audit and Assurance

Contents

Executive Summary	3

1.	Introduction	4

2.	Detailed Audit Findings	4

Appendix A: Assurance opinion and action plan risk rating	11

| Review reference: |  | DHCW-2122-07 |
| --- | --- | --- |
| Report status: |  | Final |
| Fieldwork commencement: |  | 24th January 2022 |
| Fieldwork completion: |  | 24th March 2022 |
| Draft report issued: |  | 30th March 2022 |
| Debrief meeting: |  |  |
| Management response received: |  | 4th April 2022 |
| Final report issued: |  | 6th April 2022 |
| Auditors: |  | Martyn Lewis (ICT Audit Manager) Sian Harries (ICT Auditor) |
| Executive sign-off: |  | Carwyn Lloyd Jones (Director of ICT) |
| Distribution: |  | Jamie Graham (Infrastructure Programme Manager) Martin Prosser (Head of Infrastructure Operations) Matt Palmer (Head of Infrastructure Design) |
| Committee: |  | Audit Committee |
|  | Audit and Assurance Services conform with all Public Sector Internal Audit Standards as validated through the external quality assessment undertaken by the Institute of Internal Auditors |  |
| Acknowledgement NHS Wales Audit & Assurance Services would like to acknowledge the time and co-operation given by management and staff during this review. |  |  |
| Disclaimer notice - please note This audit report has been prepared for internal use only. Audit & Assurance Services reports are prepared, in accordance with the Service Strategy and Terms of Reference, approved by the Audit Committee. Audit reports are prepared by the staff of the NHS Wales Shared Services Partnership – Audit and Assurance Services and addressed to Independent Members or officers including those designated as Accountable Officer. They are prepared for the sole use of Digital Health & Care Wales and no responsibility is taken by the Audit and Assurance Services Internal Auditors to any director or officer in their individual capacity, or to any third party. |  |  |

# Executive Summary

| Purpose To evaluate and determine the adequacy of the processes in place in DHCW for the management of the Data Centre move and the current Data Centre Service. Overview We identified no significant issues for reporting in our review. The relocation of the data centre was undertaken in a controlled manner and was successfully completed within the expected time frame. | Report Classification Substantial assurance. Few matters require attention and are compliance or advisory in nature. Low impact on residual risk exposure.. Assurance summary Assurance objectives; Assurance. 1; Project Governance; Substantial. 2; Testing; Substantial. 3; Lessons Learned / Benefits; Substantial. 4; Current Data Centre Service; Substantial. |
| --- | --- |

# Introduction

- The review of the governance arrangements in place for the Data Centre Move was completed in line with the 2021/22 Internal Audit plan for DHCW (the ‘organisation’).

- Following the end of the contract for hosting NHS Wales equipment within the Blaenavon Data Centre, the decision was made to move into a new data centre location, the CloudCentres Data Centre (CDC). The move was governed by a formal project process to ensure that all equipment and services were transferred successfully. The relevant lead for the assignment is the Director of ICT.

- The potential risks considered in the review are as follows:

- loss of processing / data; and

- inconsistencies in data centre provision impacts on service delivery across Wales.

# Detailed Audit Findings

Objective 1: Project Governance – an appropriate project governance process was in place that ensures control was maintained over the project, risks were managed and formal reporting and monitoring undertaken.

- The Data Centre Transition (DCT) Project was formed in September 2020 and progressed identified actions through three workstreams, which focussed on delivering the successful transition of systems from Blaenavon Data Centre (BDC) to the new CloudCentres Data Centre (CDC).

- The DCT Project was formal and adopted PRINCE2 methodologies. A comprehensive Project Initiation Document (PID) was authored by the DCT Principal Project Manager and approved by the Director of ICT. The PID included full project details such as:

| Project Definition | - Background - Objectives - Desired outputs and outcomes - Scope |
| --- | --- |
| Project Approach | - Structure - Workstream detail - Plan on a Page - Assumptions, constrains and dependencies |
| Project Control | - Governance - Change and Configuration Management - Roles and responsibilities - Quality and Assurance - Risks, Assumptions, Issues, and Dependencies (RAID) |

- We noted within the PID that there was a detailed governance structure inclusive of a Project Board and Project Team with clearly defined membership, roles, and responsibilities.

Project Board

- The Project Board also had representation from local Health Boards, Welsh Government, and various teams in DHCW including Technical, Finance and Procurement.

- We reviewed Project Board meeting agendas and minutes and noted that detailed discussions were held with any resulting actions and decisions recorded on separate registers.

Project Team

- The three workstreams focussed on delivering the successful transition of systems were as below, with each workstream reporting into the Project Board.

- Project Team membership was appropriate, and was comprised of:

- Extensive reporting arrangements were in place throughout the project lifecycle as defined within the Governance Meetings Matrix included as Appendix B of the PID. Meetings consisted of:

  - weekly NWIS Directors Meeting (monthly Executive Board);

  - monthly DCT: SRO Steering Board;

  - monthly DCT Project Board;

  - weekly Application Meeting;

  - weekly Procurement Meeting;

  - weekly Technical Meeting; and

  - daily Scrum.

Each group had a defined purpose, scope, reporting type, and identified key stakeholders.

- We confirm appropriate controls were in place throughout the project. We reviewed the overarching Project Transition Plan which provided a summary of key plans including:

  - Master Transition Batch Plan;

  - CDC Cabling Schedule;

  - SCC Transition Resource Plan; and

  - DHCW Network Implementation Plan.

- The Master Transition Batch Plan contains both high-level and granular detail relating to project deliverables, phases, key activities, planned timescales and resource plans with named officers against key transition activities.

- An Engagement Plan was developed which clearly defined the communication objectives, audiences, key messages, communication issues, constraints, and assumptions as well as the communication approach. We noted within the DCT Project Closure Report that positive feedback had been received regarding the communications sent by the DCT Project Team.

- The DCT Project was subject to a standard risk management process with a full RAID log maintained throughout, which captured Risks, Assumptions, Issues, and Dependencies, along with their associated mitigations. Risks and issues requiring escalation were managed through the PMO, following the project governance structure. Open risks/issues were reviewed on a monthly basis and the highest rated ones were reviewed in detail at Project Board meetings. The Board Members also reviewed and approved all key decisions.

- The majority of risks have been closed, with the outstanding risks presented to the Project Board on 16 December 2021 with supporting proposals to transfer to appropriate DHCW Teams for ongoing management and resolution. We cross-referenced the RAID Log with the outstanding risks presented to the Project Board and we can confirm all were discussed and managed appropriately.

Conclusion:

- Our review highlighted project management best practices throughout the project lifecycle. We noted extensive governance arrangements in terms of project structure, controls, and risk management, and consequently we have provided substantial assurance over this objective.

Objective 2: Testing – the project ensured that testing was appropriately undertaken, including of equipment, network links and failover.

- Testing was formally included as part of the project, with appropriate test plans in place. Testing included:

- failover ability;

- test of the new architecture after build;

- network testing; and

- power down testing for the equipment being moved.

- Testing of the architecture and network connectivity was undertaken by the consultancy provider and was ‘out of hours’ to minimise the risks of disruption. The testing of the architecture and network was split into sections related to components in the design and included redundancy testing of the network and data centres. Testing of the architecture solution was defined by a formal test plan, and completion of this was formally signed off and approved at project board.

- Testing was also undertaken on utilities within the new data centre. There was load bank testing to ensure that the backup power supply was appropriate and testing of the cooling systems.

- Testing was also undertaken on each system as it was moved across to ensure availability and connectivity for users. This was a formalised process with the relocation stages set out in plans which noted the power cycle test on Fridays and the application testing on Sundays.

- Detailed plans were developed for the move, which included testing, which was undertaken by application teams once the move and infrastructure items had been completed. The progress of the application testing was tracked and recorded by the project manager, and success confirmed in post-move meetings.

Conclusion:

- Testing was included within the project plan and test plans were defined and completed. All testing was signed off as complete, and accordingly we have provided substantial assurance for this objective.

Objective 3: Lessons Learned / Benefits – a process is in place to identify lessons from the data centre move and to ensure that identified benefits are realised.

- The project has been subject to a full post implementation review, which included a process to identify lessons that can be factored into future projects.

- Following this a formal closure report was produced, this was finalised in January 2022 and approved by the lead director. The closure report reviews the performance of the project, with the key items included within the report being:

- noting the delivery of the project scope and all objectives in the PID;

- assesses project performance against the objectives and notes a positive outcome;

- assesses project performance against the stated outputs and notes a positive outcome;

- assesses project performance against outcomes (benefits), and notes a positive outcome;

- assesses project performance against costs, and notes a forecast underspend of £2.2k;

- assesses project performance against timescales, and notes a generally positive outcome whilst providing information on delays due to covid and complexity;

- breaks down the tasks contained within the project by workstream and assesses status; and

- notes the creation of a lessons learned log.

- Meetings with stakeholders and workshops were held, together with questionnaires used to capture lessons in order to improve future projects. We note that there were over 180 identified lessons, and these have been categorised by theme and used to create specific recommendations for the organisation.

- These lessons were compiled into the closure report, and also into single slides for rapid reporting. These were reported both to the Project Board, but also to Management Board and Directors to enable the wider sharing of learning.

- A process is in place to ensure that lessons are taken forward and embedded in future projects.

- For recommendations that are pertinent to the next data centre project, there are to be a series of workshops with each of the subgroups to ensure that the lessons are carried forward into the project. In addition, the lessons are to be the focus of a workshop with the third-party networking consultants in early April 2022.

- For recommendations that have wider organisational learning, these are grouped into six wider themes, and they will be shared with and discussed at the Incident Review and Learning Group.

- We note that the project was not necessarily a benefit led project, but it was required as the data centre provider was terminating the service, and so a move to a new location had to happen. This required move was used as an opportunity to improve the provision in the new location.

- Benefits were identified in the PID and were defined as the desired outcomes and comprised:

- continued delivery of on-prem infrastructure;

- upgrading of network infrastructure; and

- roadmap to cloud adoption.

- The benefits as set out in the PID have largely been achieved, with the new data centre being active as anticipated. The network within the new data centre is a software defined network and this provides greater bandwidth, resiliency, and growth capacity. It also allows for better flexibility in how network resources are deployed.

- The roadmap to cloud adoption has not been achieved. However, the data centre project was used to demonstrate the capability of cloud, and a Cloud Strategy Programme has been established to develop the roadmap, and this will use information from the data centre project.

Conclusion:

- The project considered the benefits to be achieved from the data centre re-location, and these have largely been realised, with a new data centre active and an upgraded network provision. A post implementation review has been undertaken that assessed the project and which identified lessons to be used in future projects with DHCW, and there is a mechanism for ensuring that this learning is shared appropriately. Accordingly, we have provided substantial assurance for this objective.

Objective 4: Current Data Centre Service– the current data centre service provision is consistent across sites, has appropriate risk management, is modern and appropriate to the need of NHS Wales.

- We note that both data centres now sit within the same tier and so will provide the same level of controls over access and resilience. The differences between the two sites are related to the network provision, with the new data centre having a modern, software defined network, and the older (Newport) data centre retaining a traditional hardware based network.

- We note therefore, that the technology in use within the new data centre is more current than the Newport data centre and so will have greater longevity. The project included the use of a consultancy to design and build the new network (Cisco ACI network). As the provider is an accredited member of Ciscos’ Partner Support Service, DHCW has confidence that the network architecture is fully compliant with Ciscos’ recommended network implementation.

- The risk relating to the differences between the data centres is clearly identified, and relates to the divergence in network configuration, which is likely to increase over time and impact on the ability of DHCW to provide rapid disaster recovery and delay recovery times.

- A Situation-Background-Assessment-Recommendation document (SBAR) has been produced that clearly articulates the network risks and provides options and potential solutions. We note that the contract for the Newport data centre ends in the near future, and so work on phase two of the data centre project has commenced and is looking at options for improving the provision relating to this data centre.

- Due largely to the network provision within the new data centre, there is greater scalability and so a greater ability to meet the future needs of NHS Wales, and this is one of the factors considered within the options assessment relating to the Newport data centre.

Conclusion:

- The current data centre provision for DHCW provides a largely consistent service in terms of resilience and hosting environment. There are differences now extant in networking and scalability and there is a risk associated with this which is appropriately articulated. The contract for the Newport data centre is coming to an end and the network risk is being considered as one of the factors in the option appraisal. Accordingly, we have provided substantial assurance for this objective.

# Appendix A: Assurance opinion and action plan risk rating

Audit Assurance Ratings

We define the following levels of assurance that governance, risk management and internal control within the area under review are suitable designed and applied effectively:

|  | Substantial assurance | Few matters require attention and are compliance or advisory in nature. Low impact on residual risk exposure. |
| --- | --- | --- |
|  | Reasonable assurance | Some matters require management attention in control design or compliance. Low to moderate impact on residual risk exposure until resolved. |
|  | Limited assurance | More significant matters require management attention. Moderate impact on residual risk exposure until resolved. |
|  | No assurance | Action is required to address the whole control framework in this area. High impact on residual risk exposure until resolved. |
|  | Assurance not applicable | Given to reviews and support provided to management which form part of the internal audit plan, to which the assurance definitions are not appropriate. These reviews are still relevant to the evidence base upon which the overall opinion is formed. |

Prioritisation of Recommendations

We categorise our recommendations according to their level of priority as follows:

| Priority level | Explanation | Management action |
| --- | --- | --- |
| High | Poor system design OR widespread non-compliance. Significant risk to achievement of a system objective OR evidence present of material loss, error or misstatement. | Immediate* |
| Medium | Minor weakness in system design OR limited non-compliance. Some risk to achievement of a system objective. | Within one month* |
| Low | Potential to enhance system design to improve efficiency or effectiveness of controls. Generally, issues of good practice for management consideration. | Within three months* |

* Unless a more appropriate timescale is identified/agreed at the assignment.

NHS Wales Shared Services Partnership 4-5 Charnwood Court Heol Billingsley Parc Nantgarw Cardiff CF15 7QZ Website: Audit & Assurance Services - NHS Wales Shared Services Partnership

The objectives and associated assurance ratings are not necessarily given equal weighting when formulating the overall audit opinion.

PID-DCT_ProjectInitiationDoc, 3.1 Structure