## Slide 1
Corporate Planning | Project Portfolio Q1(1/4)
Key | Alerts | Finance |  | Resourcing and/or skills |  | Scope | 
 |  | Timescale |  | Dependencies |  | Agile | 
RAG Definition | Good may require refinement | Requires attention | Highly Problematic
RAG Scores : please note these are applied by external Governance Boards not DHCW and relate to all aspects of the project, not just the DHCW deliverables
Status remains same
Status improving
Status deteriorating
Portfolio | Product |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Governance | RAG
Information Availability and Flow | National Data Resource Supporting health and care in Wales to be innovative, modern and using data to drive decisions | Initiate | Define |  | Define |  |  | Build |  |  |  | External Build | Roll Out Google Cloud Platform Procurement live June 2022. Award expected Q3. Additional work packages for infrastructure design and implementation currently being defined Open Architecture has three projects underway: API Management, FHIR standards and Clinical Data Engine Advanced Analytics sub-Strategy being developed during Q3 with the latest Analytics Learning Programme launched June 2022 NDR Data Strategy live |  |  |  |  |  |  |  |  | National Data Resource Programme Board SRO: John Peters DHCW Director: Rebecca Cook | 
 |  | Cloud Platform |  |  |  |  |  |  |  |  |  | Internal Build |  |  |  |  |  |  |  |  |  |  | 
 |  | Open Architecture |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Advanced Analytics |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Data Strategy |  |  |  |  |  |  |  |  |  |  | Next Major Milestone: Implementation Plan for Delivery of Data Strategy Q2 2022/23 |  |  |  |  |  |  |  |  |  | 
Information Availability and Flow | Data Centre Transition Project Phase 2 Transition of infrastructure and services from legacy data centres to new data centres and cloud | Initiate | Define |  | Define |  |  | Build |  |  |  |  | Roll Out Replacement Data Centre requirements and specification complete. High-level Design for new network environment and infrastructure expected by Q2 2022/23. |  |  |  |  |  |  |  |  | Data Centre Transition Project Board SRO: Carwyn Lloyd Jones DHCW Director: Carwyn Lloyd Jones | 
 |  | Data Centre 2 Procurement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Architecture and Networking |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Resilience and Transition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Digital Professional Empowerment | Cancer Informatics Programme Replacing the legacy cancer system (Canisc) across Wales | Initiate | Define |  | Define |  |  | Build |  |  |  | Internal Build | Roll Out A new go live date has been agreed with VCC for 14 Nov 22. Health Boards plan to launch dataset forms for two cancer tumours across Wales in Sept 2022. A number of MDT and Dataset forms are currently in UAT across Wales. ​Next Major Milestone: Product Available (National) – Initial Iteration for Cancer Solution July 2022 (awaiting programme board approval) |  |  |  |  |  |  |  |  | Cancer Informatics Programme Board SRO: Tracey Cooper DHCW Director: Rhidian Hurle | 
 |  | Patient Administration Functionality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Clinical Functionality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | RAG reason: Scope & Timescales extended | 
Digital Professional Empowerment | Electronic Test Requesting Expanding electronic test requesting to new disciplines and improving existing electronic test requesting functionality. | Initiate | Define |  | Define |  |  | Build |  |  |  | Internal Build | Roll Out Radiology e-form V2 now live in CTM & BCU. SBUHB, ABUHB and VCC to take V2 by Q3. New Histopathology e-form to be live in BCU Q2 2022/23 and a Phlebotomy module pilot to start in Q2. Result notifications now live in all health boards (bar AB and Powys - out of scope) Next Major Milestones: New Cardiology e-form to be live Q4, Radiology V3 live in Q3, and Radiology in Primary Care workflow and technical design to be agreed by Q2. |  |  |  |  |  |  |  |  | Electronic Test Requesting Project Board SRO: Rob Bleasdale DHCW Director: Rhidian Hurle | 
 |  | Cardiology, Phlebotomy, Histopathology |  |  |  |  |  |  |  | Radiology requests (Cwm Taf & BCU) |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Cardiology, Phlebotomy, Histopathology |  |  |  |  |  |  |  | Radiology requests (Cwm Taf & BCU) |  | Radiology requests (Cwm Taf) |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  | Pathology test requesting / Results Notifications | Pathology test requesting / Results Notifications |  |  |  |  |  |  | RAG reason: Resource diverted to Covid for some modules | 
Project Completion Nov 2022 – at risk

## Slide 2
Corporate Planning | Project Portfolio Q1(2/4)
Portfolio | Product |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Governance | RAG
Digital Professional Empowerment | Welsh Information System for Diabetes Management Using Welsh Clinical Portal to record diabetes data | Initiate |  |  | Define | Define |  |  |  | Build |  |  |  |  |  | Internal Build | Roll Out Current modules – adult, podiatry and antenatal. Paediatrics design is completed, now in development. Next major milestone: Paediatrics Forms Q3 2022/23 |  |  |  |  |  |  |  |  |  | Welsh Information System for Diabetes Management Project Board (Reports to Diabetes Implementation Group) SRO: Phil Evans DHCW Director: Rhidian Hurle | 
 |  |  |  |  | Paediatrics | Paediatrics |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Adult, Podiatry and Antenatal (Cwm Taf Morgannwg, Hywel Dda and Swansea Bay) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Digital Professional Empowerment | Welsh Nursing Care Record Enables nurses to complete electronic assessments at hospital bedsides | Initiate |  |  |  | Define |  |  |  | Build |  |  |  |  |  | Internal Build with Swansea Bay | Roll Out Live in 6 health boards CAV implementation planned to start in Q2. AB planned for Q3/Q4 2022/23. HB/Trusts agree with Single Instance approach but “not now”. As a result v2.2 is delayed and now scheduled for Q3. Next Major Milestone: v2.2 scheduled for Q3 2022/23. |  |  |  |  |  |  |  |  |  | Welsh Nursing Care Record (WNCR) Project Board SRO: Claire Bevan DHCW Director: Rhidian Hurle | 
 |  |  |  |  |  |  |  | Velindre, Swansea Bay, Hywel Dda, Powys, Cwm Taf, Betsi | Velindre, Swansea Bay, Hywel Dda, Powys, Cwm Taf | Velindre, Swansea Bay, Hywel Dda, Powys, Cwm Taf |  |  |  |  |  |  |  |  | 2 sites not yet live and scale of implementation is significant |  |  |  | At least until March 2023. 3 sites not yet live and scale of implementation is significant |  |  |  | RAG reason: Delay to full agreement of Single Instance approach | 
Digital Patient Empowerment | Digital Services for Patients and the Public Patient facing app improving patient access to services and data | Initiate |  |  |  | Define |  |  |  | Build |  |  |  |  |  | External Build | Roll Out Work Package 3 Phase 2 build complete in June 22. Next Major Milestone: Work Package 4 (pending contract signature) |  |  |  |  |  |  |  |  |  | Digital Services for Patients and Public Programme Board (plus 7 national assurance groups) SRO: Huw George DHCW Director: Michelle Sell | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | RAG reason: capacity /dependencies/ resources to deliver in line with supplier agile approach/ Access to NHS Login in Welsh /finance not confirmed | 
Public Health | Test Trace and Protect Covid-19 testing, contact tracing and vaccination data solutions | Initiate |  |  |  | Define |  |  |  | Build |  |  |  |  |  | External Build | Roll Out Implementation complete of Covid test requesting, contact tracing, Immunisation System, 2 way texting and Covid Pass but new requirements are being requested due to changes in policy. Next Major Milestone: Autumn boosters Q2 2022/23 |  |  |  |  |  |  |  |  |  | Digital Pathway Group. SRO: Ifan Evans / Helen Thomas DHCW Director: Helen Thomas Test Trace Protect Policy and Delivery Board Vaccination Programme Board Contact Tracing Task & Finish Group Test Trace Protect Programme Oversight Group | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Internal Build |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Contact Tracing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | All Health Boards and local authorities |  | All Health Boards and local authorities |  |  |  |  |  | 
 |  | Immunisation Recording |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | All Health Boards & Primary Care |  | All Health Boards |  |  |  |  | RAG reason: resource constraints, enlarged scope, volume of new requirements | 
Project completion / handover to BAU Mar 2023
Project Completion Mar 2023

## Slide 3
Corporate Planning | Project Portfolio Q1(3/4)
Portfolio | Product |  |  |  |  |  |  |  |  | Governance | RAG
Primary, Community and Mental Health | Choose Pharmacy System to record enhanced services provided by community pharmacists. | Initiate | Define | Build |  | Internal Build | Roll Out Roll out complete but existing modules continually enhanced and new modules added. Next Major Milestone, Release Available – Implement Changes to flu module, Q2 2022/23 Release Available – Bridging contraception, Q2 2022/23 |  |  | Community Pharmacy Digital Applications Programme Board Choose Pharmacy Service Management Board SRO: Jenny Pugh-Jones DHCW Director: Carwyn Lloyd-Jones | 
 |  |  |  |  |  |  | All Health Boards |  |  | RAG reason: Resource movement due to Covid priorities. | 
Primary, Community and Mental Health | Dental E Referrals providing dental referral system for community dentists. | Initiate | Define | Build |  | External Build | Roll Out Phase 2 integration work on hold Contract with system supplier due to expire in 2023 Procurement project in progress Next Major Milestone, Product Available (Early Adopter) Q4 2022/23 - this work is on hold |  |  | Dental Referral Management System Project Board for re-procurement SRO: Alex Slade DHCW Director: Carwyn Lloyd-Jones | 
 |  | New project – re-procurement |  |  |  |  |  |  |  | RAG reason: Integration delayed due to internal resource constraints. | 
Primary, Community and Mental Health | GP Systems Framework Implementation of systems to GP practices, including any necessary integrations and developments. | Initiate | Define | Build |  | External Build | Roll Out Deployment orders prepared and awaiting signature. A number of developments in progress under current contractual arrangements - dependency on suppliers leading to delays to plans. Next Major Milestone, Migration Complete Mar 2023 |  |  | General Medical Services (GMS) IM&T Programme Board SRO: Lisa Dunsford DHCW Director: Carwyn Lloyd Jones | 
 |  | Framework Contracts signed for all 3 suppliers |  |  |  |  |  |  |  | RAG reason: Supplier delays for new developments. | 
Primary, Community and Mental Health | Welsh Community Care Information System Community information solution for community health, mental health staff and social workers | Initiate | Define | Build |  | External Build | Roll Out 3 Health Boards live (Cwm Taf Morgannwg, Powys and Hywel Dda), 3 further in pipeline (Aneurin Bevan, Betsi Cadwaladr, Swansea Bay). 15 Local Authorities live. Next Major Milestone: Aneurin Bevan Phase 1 Mental Health – Q2 2022/23 |  |  | WCCIS Leadership Board (plus 4 sub boards) SRO: Carol Shillabeer / Dave Street DHCW Director: Ifan Evans | 
 |  |  |  | Health – Cwm Taf Morgannwg, Powys and Hywel Dda |  | Health – Cwm, Taf Morgannwy, Powys and Hywel Dda |  |  |  | RAG reason: ABUHB implementation delay due to legacy system issues | 
Planned and Unscheduled Care | Welsh Emergency Dept System Implementing a managed service with EMIS Health. DHCW responsible for hosting, integration with other national systems and managing the national contract. | Initiate | Define | Build |  | External Build | Roll Out Swansea Bay live at first site in Dec 2021. Morriston go live date to be agreed. Cwm Taf Morgannwg local implementation now paused due to resource and support issues. Roll out in other Health Boards subject to demonstration of success in SBU and WEDS Acceleration (DPIF) funding by Welsh Government.​ Next Major Milestone: Go-live CTM 2022/23 |  |  | National WEDS Project Board SRO: Jo Mower DHCW Director: Michelle Sell | 
 |  | Cwm Taf Morgannwg |  | Cwm Taf Morgannwg |  |  |  |  |  |  | 
 |  |  |  |  |  |  | Swansea Bay |  |  | RAG reason: Service performance issues, resource challenges in HBs, DPIF uncertainty | 

## Slide 4
Primary Care –Electronic Prescription Service
Secondary Care E-prescribing and Medicines Administration
Patient Access to Medicines
Shared Medicines Record
Corporate Planning | Project Portfolio Q1(4/4)
Portfolio | Product |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Governance | RAG
Planned and Unscheduled Care | Welsh Intensive Care Information System Implementation of fully managed digital solution for Adult Intensive Care Units | Initiate |  | Define |  |  |  |  | Build |  |  |  | External | Roll Out Aneurin Bevan will be the first to implement in Jan 2023 and then a roll out to all HBs. Reprofiled costs agreed with DPIF (10% reduction). VAT recovery status being investigated by Ernest Young. |  |  |  |  |  |  |  | Welsh Intensive Care Information System Programme Board SRO: Mark Dickinson DHCW Director: Michelle Sell | 
 |  |  |  |  |  |  |  |  |  |  |  |  | Build |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  | Next Major Milestone: Complete User Acceptance Testing Dec '22 |  |  |  |  |  |  |  | RAG reason: Dependency on National Subscription Service (diagnostic result visibility) | 
Diagnostics | Radiology Informatics Solution Procurement of an end-to-end diagnostic radiology system to meet the clinical requirements of a modern imaging service | Initiate |  | Define |  |  |  |  | Build |  |  |  | External | Roll Out Outline Business Case approved, procurement started. |  |  |  |  |  |  |  | Radiology Informatics Solution Programme Board SRO: Matt John DHCW Director: Michelle Sell | 
 |  |  |  |  |  |  |  |  |  |  |  |  | Build |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  | Next Major Milestone |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  | Complete Procurement Jan 2023 |  |  |  |  |  |  |  | RAG reason: Delay in Business Case approval means project behind schedule to complete before legacy contract end date | 
Diagnostics | Welsh Imaging Archive Service Medical image sharing across Wales | Initiate |  | Define |  |  |  |  | Build |  |  |  | External | Roll Out Pilots planned with Swansea Bay and Velindre. No dates confirmed. Architecture approach under review. |  |  |  |  |  |  |  | Welsh Imaging Archive Service Project Board SRO: None DHCW Director: Rhidian Hurle | 
 |  |  |  |  |  |  |  |  |  |  |  |  | Build |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  | Next Major Milestone |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  | Build complete Q3 2022/23 |  |  |  |  |  |  |  | RAG reason: milestone at risk. | 
Medicines Management | Digital Medicines Transformation Portfolio (DMTP) Designing new programme to modernise prescribing services across primary, community and secondary care. | Initiate |  | Define |  |  |  |  | Build |  |  |  | External | Roll Out |  |  |  |  |  |  |  | Governance being established | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  | Programme and projects currently being defined and agreed, recruitment for key posts underway. |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | Build |  |  |  |  |  |  |  |  | DMTP Sponsoring Group and Portfolio Board established. SRO: Hamish Laing DHCW Director: Ifan Evans | N/A at this stage
 |  |  |  |  |  |  |  |  |  |  |  |  |  | Next Major Milestone |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  | Contract Award for Framework (for ePMA solution) scheduled for Qtr 3 22/23 (Request for Change submitted) |  |  |  |  |  |  |  | Inaugural Shared Medicines Record programme board to be held in July. | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  | Invitation To Tender for Electronic Prescribing and Medicines Administration Framework to be re-published. Contract Award timescales to be confirmed |  |  |  |  |  |  |  | Inaugural Primary Care Electronic Prescription Service programme board held. | 
Primary Care Electronic Prescription Service
Secondary Care E-prescribing and Medicines Administration
Patient Access to Medicines
Shared Medicines Record
Project Completion
Jun 2024
Project Completion
Jun 2025