Item 5.2i Appendix 1

Digital Health and Care Wales

External Stakeholder Engagement

Draft Action Plan

2021/22 – 2023/24

Version 0.4 | 15 December 2021

- Introduction

The Board of Digital Health and Care Wales approved their first Engagement Strategy on 30th September 2021. It is  set out in eight sections:

- Strategic context

- Methodology

- Our engagement:  purpose, scope, aims and objectives

- What will we engage our stakeholders on?

- Who are our stakeholders?

- Our approach to engagement

- Developing and delivering our engagement plan

- Performance review

In approving the strategy, it was recognised further work was required to develop an engagement plan (section seven of the published strategy document). By March 2022 we will also put in place a performance framework to assess whether we have met our engagement objectives and implemented our engagement plan for 2022/23. This will consider both process measures (what engagement activities we took) as well as outcome measures (contribution to delivery of Annual Plan and organisational objectives). This is likely to include commissioning a sentiment survey with stakeholders. The outputs from Focus Groups and stakeholder interviews carried out in  2021/22 by the Consultation Institute will provide baseline information in relation to corporate reputation and strategic direction. This will be repeated in 2022/23.

The purpose of this document is to set out an Action Plan to support the implementation of the Strategy. It covers some preparatory actions (2021/22) and details for Year one (2022/23) and with some forward planning for year two (2023/24).

As a board our strong belief is that by successfully  implementing our external stakeholder engagement strategy it will contribute to meeting Digital Health and Care Wales’s  objectives. In turn this will contribute to the wider delivery of health and social care across Wales.

Scope, aim and objectives of our stakeholder engagement strategy and action plan

The focus of our strategic engagement activities is on our external stakeholders with an overall aim to achieve a higher level of collaboration creating opportunities to both influence and be influenced. To deliver this we have set out four objectives:

- To achieve a proficient level of awareness and understanding of our work among stakeholders

- To influence the work of our stakeholders

- To provide effective opportunities for stakeholders to influence our work

- To explain where stakeholder input was effective and, where it has not

Developing our overarching Board Strategy and understanding our partners priorities will prompt further refinement. The plan will need to remain flexible to reflect to any changes in priorities or other relevant strategies and circumstances. The Engagement Plan will, therefore, be regularly refreshed as well as annually through our appropriate board governance structures, and in partnership with stakeholders. Strategic Internal engagement will also need to be discussed. The structure of the Plan is as follows:

| Action Plan Headings | Description |
| --- | --- |
| Theme | Actions have been grouped in the plan under a series of themes as described in the Action Plan. |
| Actions required | Specific actions currently identified to implement the stakeholder engagement strategy. |
| Stakeholders | Actions aligned to specific stakeholders broken down by categories and profiles as set out in the engagement strategy. |
| Engagement Approaches | Specific method(s) that will be used to engage with stakeholders. This will vary depending on the purpose and the stakeholders using digital and non-digital approaches. |
| Lead(s) | Senior member of Digital Health and Wales with strategic responsibility for ensuring timely delivery or adjustments. Three of the identified ‘leads’ are currently not in position: Director of Digital Strategy, Director of People and Engagement Lead. Interim arrangements will be put in place should there be delays in making appointments. |
| Partner(s) | External organisations where collaboration has been agreed such as Health Education and Improvement Wales. |
| Timescale | Each action or suite of actions has been assigned an indicative timescale aligned to planning year: Q1 (Apr-Jun); Q2 (Jul-Sep); Q3 (Oct-Dec); Q4 (Jan-Mar). |

Draft Action Plan | Preparatory Year one (2021/22)

| Theme | Action required | Stakeholders | Engagement Approaches | Lead(s) / Partners | Timescale |
| --- | --- | --- | --- | --- | --- |
| Ref 1/ 1.1 A-Communications | - Ensure Communications Strategy links with Engagement Strategy. | Internal |  | Board Secretary Head of Communications | Year 1 Q4 (Jan–Mar) |
| Ref 1/1.2 A-Communications | - Establish process for ongoing discussion around Digital Health and Care Wales planning and priorities. | NHS Wales Organisations Welsh Government Patient and Public | Online fora | Board Secretary Head of Communications | Year 1 Q4 (Jan–Mar) |
| Ref 1/ 1.3 A-Communications | - Oversee development of key messages to support implementation of Engagement Strategy. | Internal NHS Wales Organisations Welsh Government |  | Chair / Chief Executive Board Secretary Head of Communications Independent Member | Year 1 Q4 (Jan–Mar) |
| Ref 1/ 1.4 A-Communications | - Oversee publication of Stakeholder Engagement Strategy and Plan with any appropriate graphics (including Welsh language). | NHS Wales Organisations Welsh Government Patient and Public |  | Chief Executive Board Secretary Head of Communications | Year 1 Q4 (Jan–Mar) |
| Ref 1/ 1.5 A-Communications | - Prepare for, sign up and then promote the Welsh National Digital Inclusion Charter. | Internal Patients and Public Assurance Group | Internal Newsletters Social Media | Chief Executive / Chief Operating Officer Digital Communities Wales Digital Inclusion Alliance Wales | Year 1 Q4 (Jan–Mar) Year 2 Q1 |
| Ref 1/ 1.6 A-Communications | - Scope approach to strengthen relationships with media. | Internal |  | Chair / Chief Executive Board Secretary Head of Communications Independent Member | Year 1 Q4 (Jan–Mar) |
| Ref 1/ 2.1 B-Engagement -Strategic | - Agree programme of work with Patients and Public Assurance Group. | Patients and Public Assurance Group | Discussion at Group | Chief Operating Officer/National Clinical Informatics Lead - Public | Year 1 Q4 (Jan–Mar) |
| Ref 1/ 2.2 B-Engagement -Strategic | - Align Digital Health and Care Wales strategies with that of partners to collectively understand direction of travel. | NHS Wales Organisations Welsh Government | Established regular meetings | Chair / Chief Executive / Board Secretary | Year 1 Q4 (Jan–Mar) Year 2 Q1 (Apr–Jun) |
| Ref 1/ 2.3 B-Engagement -Strategic | - Align Management Board Members with Welsh Government Policy Leads. | Welsh Government | Established regular meeting | Chair / Chief Executive | Year 1 Q4 (Jan–Mar) |
| Ref 1/ 2.4 B-Engagement -Strategic | - Align Stakeholder Engagement Plan to existing meetings and fora. | As per Stakeholder Maps | Established regular meetings | Chief Operating Officer / Board Secretary | Year 1 Q4 (Jan–Mar) |
| Ref 1/ 2.5 B-Engagement -Strategic | - Create and support the Independent Members Digital Network with NHS Wales. | Internal NHS Wales Organisations Welsh Government | Established regular meeting | Chair / Independent Members / Chief Executive / Board Secretary | Year 1 Q4 (Jan–Mar) Year 2 Q1 (Apr–Jun) |
| Ref 1/ 2.6 B-Engagement -Strategic | - Develop approaches based on the Digital Services for Patient and Public engagement work to promote involvement and user insights. | As per Stakeholder Maps | ‘Get Involved’ focus groups On-line feedback routes Surveys | Patients and Public Assurance Group National Clinical Informatics Lead - Public | Year 1 Q4 (Jan–Mar) Year 2 Q1 (Apr–Jun) |
| Ref 1/ 2.7 B-Engagement -Strategic | - Engage on future strategic direction (Annual Plan, Strategy refresh etc). | NHS Wales Organisations Welsh Government | Established regular meeting Workshops | Chair / Chief Executive / Chief Operating Officer / Board Secretary | Year 1 Q4 (Jan–Mar) Year 2 Q1 (Apr–Jun) |
| Ref 1/ 3.1 C-Equalities, Inclusion, and accessibility | - Build links to understand the current requirements to support digital inclusion. | Digital Communities Wales Patients and Public Assurance Group | Meetings and workshops Feedback from established groups | Chief Operating Officer National Clinical Informatics Lead - Public | Year 1 Q4 (Jan–Mar) Year 2 Q1 (Apr–Jun |
| Ref 1/ 5.1 F-Stakeholder Management | - Ongoing Stakeholder Mapping including. | As reflected in Stakeholder maps | Meetings and small workshops | Chief Operating Officer | Year 1 Q3 (Oct–Dec) Year 1 Q4 (Jan–Mar) |
| Ref 1/ 5.2 H-Governance | - Agree Job Description, Resources etc to appoint Engagement Lead. | Internal | Interview | Chief Operating Officer | Year 1 Q4 (Jan–Mar) Year 2 Q1 (Apr–Jun) |
| Ref 1/ 7.1 H-Governance | - Approve Stakeholder Engagement Plan. | Board Meeting | Board Development Board Meeting 27 January | Chief Operating Officer | Year 1 Q3 (Oct-Dec) Year 1 Q4 (Jan–Mar) |
| Ref 1/ 7.2 H-Governance | - Develop Performance Framework. | NHS Wales Organisations Welsh Government Research and Evaluation Bodies | Board Development Board Meeting 31 March | Project Group overseeing delivery | Year 1 Q4 (Jan–Mar) Year 2 Q1 (Apr–Jun) |
| Ref 1/ 7.3 H-Governance | - Establish small project group to oversee implementation of Action Plan including measure and monitoring. | Internal | One to one discussions Workshops | Chief Operating Officer | Year 1 Q4 (Jan–Mar) |
| Ref 1/ 7.4 | - Review Executive Leads overseeing sections of the Action Plan. | Executive Directors | Executive Director Meetings | Chief Executive | Year 1 Q4 (Jan–Mar) |

Year two (2022/23) and Year three (2023/24)

| Theme | Action required | Stakeholders | Engagement Approaches | Lead(s) / Partners | Timescale |
| --- | --- | --- | --- | --- | --- |
| Ref 2/ 1.1 A-Communications | - Publish Stakeholder Engagement Strategy and Plan. | NHS Wales Organisations Welsh Government Patient and Public | Direct email to named leads, information on Digital Health and Care Wales website, news item including link to register interest | Chief Executive / Board Secretary / Head of Communications | Year 2 Q1 (Apr -Jun) |
| Ref 2/ 1.2 A-Communications | - Develop Patient and Public ‘Get Involved’ focus group based on the Digital Services Patient and Public engagement work and invite public to register to be involved. | Patients and Public Assurance Group | Digital Health and Care Wales website as a channel for patients to register interest Non digital approaches (Free Post, phone) | Chief Executive / Head of Communications Engagement Lead National Clinical Informatics Lead - Public | Year 2 Q1 Apr -Jun) |
| Ref 2/ 1.3 A-Communications | - Establish dedicated ‘Get Involved’ feedback process. | Patients and Public | Digital Health and Care Wales website | Chief Executive / Board Secretary / Head of Communications | Year2 Q1 (Apr -Jun) |
| Ref 2/ 1.4 A-Communications | - Feedback to stakeholders about outputs from online forums. | Specific groups within NHS Wales and Welsh Government | Email to participants Digital Health and Care Wales website, news item, social media | Chief Executive / Board Secretary / Head of Communications | Year 2 Q3 (Oct-Dec) Q4 (Jan-Mar) |
| Ref 2/ 1.5 A-Communications | - Publish Digital Health and Care Strategy. | As set out in Stakeholder Maps (Categories and profiles) | Email direct to external leads as identified in strategy Promote via website, social, newsletter, news items | Chair and Chief Executive / Board Secretary Director of Strategy | Year 2 Q1 (Apr -Jun) |
| Ref 2/ 2.1 B-Engagement – strategic | - Continue programme of work with Patient and Public Assurance Group and identify and prioritise topics. | Members of Group | Discuss at Meetings Invite Independent Members to contribute | Exec Director of Strategy / Director of Planning and Performance / National Clinical Informatics Lead – Public | Year 2 Q1 (Apr -Jun) |
| Ref 2/ 2.2 B-Engagement – strategic | - Independent Member Digital Network. | Independent Members of NHS Wales bodies | Virtual Meetings | Independent Members | Year 2 Q1 (Jul - Sep) |
| Ref 2/ 2.3 B-Engagement – strategic | - Confirm alignment of Digital Health and Care Wales Management Board members with Welsh Government Policy Leads. | Welsh Government | Discuss at Meetings | Chief Executive / Exec Director of Strategy | Year 2 Q1 (Apr - Jun) |
| Ref 3/ 2.4 B-Engagement – strategic | - Co-produce future draft engagement strategies and plans. | To be prioritised after Year one review | To be prioritised after Year one review | Exec Director of Strategy / Director of Planning and Performance / Board Secretary Engagement Lead | Year 3 |
| Ref 2/ 2.5 B-Engagement – strategic | - Promote secure online forums for discussion around planning and priorities and delivering national systems and services. | Specific groups within NHS Wales and Welsh Government As above | Email invitation sent to all who have registered interest Online forums | Head of Communications | Year 2 Q1 (Apr - Jun) Q3 (Oct - Dec) |
| Ref 2/ 2.6 B-Engagement – strategic | - Explore options for having a National Stakeholder Advisory Group to support engagement on digital delivery of services. | Patient and Public Assurance Group Organisations with responsibilities for engagement | Initial discussions to seek views and scope out approach | Chair / Chief Executive / Exec Director of Strategy / NHS Wales organisations | Year 3 |
| Ref 3/ 2.7 B-Engagement – strategic | - To engage on future strategic directions (Annual Plan, Strategy refresh, Workforce etc). | Strategic Partners | Regular Meetings Workshops Stakeholder Interviews One to One | Chair and Chief Executive / Exec Director of Strategy / Welsh Government | Year 2 In line with planning cycles |
| Ref 2/ 3.1 C-Equalities, Inclusion, and accessibility | - Build links to understand issues to support digital inclusion. | Patients and Public Assurance Group / Organisations with responsibilities for engagement | Co-produce via online workshops + one-to-one interviews and non-digital approaches | Chief Executive / Exec Director of Strategy / Director of People & OD / Engagement Lead / National Clinical Informatics Lead – Public / Digital Communities Wales | Year 2 Q1, Q2, Q3, Q4 |
| Ref 2/ 3.2 C-Equalities, Inclusion, and accessibility | - Identify and address issues relating to Equalities, Inclusion, and Accessibility to highlight patient and the public perspective. | Patients and the Public Digital Health and Care Wales staff Board members | Discussion as part of Digital Services Patient and Public programme | Engagement Lead National Clinical Informatics Lead – Public / Patients and Public Assurance Group Digital Communities Wales | Year 2 Q1, Q2, Q3, Q4 |
| Ref 2/ 4.1 D-Leadership and Skills | - Build the knowledge and skills within the system to improve digital capabilities and leadership. Links with Workforce Strategy (internal and external). Report on initial findings. | Professionals / providers / / Health Education and Improvement Wales Wales Institute for Digital Information |  | Director of People & OD | Year 2 Q4 (Jan-Mar) |
| Ref 2/ 4.2 D-Leadership and Skills | - Understand user insights and preferences. | Patients and the public (patients, public, carers) | Co-design User-centred design Feedback surveys Events | Exec Director of Operations / National Clinical Informatics Lead – Public Patients and Public Assurance Group | Year 2 Q3 (Oct-Dec) |
| Ref 2/ 4.3 D-Leadership and Skills | - Continue to build relationship with prioritised stakeholders in a phased way. | NHS Wales organisations Welsh Government and Chief Digital Office | One-to-one meetings Participation at NHS Board meetings Events | Chair and Chief Executive (Digital Health and Care Wales Board Members) Executive Team | Year 2 Q1, Q2, Q3, Q4 |
| Ref 3/ 4.4 E-Evaluation, Innovation and Research | - Agree frameworks for specific programmes including data gathering including insights to assess benefits, address barriers, and outcomes of digital approaches baseline. | Bespoke to Programme Identify any common issues | Quantitative and Qualitative; Internal and Commissioned. | Exec Director of Finance / Working Group for Programme Benefits | Year 3 |
| Ref 3/ 4.5 E-Evaluation, Innovation and Research | - Assess recognised exemplar organisations with which to measure against our reputation and success. | Health Education and Improvement Wales Centre for Digital Public Services Organisations like Digital Health and care Wales outside Wales | To be scoped | Chair / Chief Executive / Medical Director | Year 3 |
| Ref 2/ 4.6 E-Evaluation, Innovation and Research | - Collaborate with other digital programmes in Wales and beyond. | (TEC) Cymru Health Care Research Wales Bevan Commission Research, Innovation, Improvement Centre Hubs Leads Health Technology Wales NHSX NHS Digital International | Establish Networks Review and share findings | Exec Director of Strategy / Medical Director / Working Group for Research and Innovation Wales Institute for Digital Information | Year 2 Q1,Q2, Q3, Q4 |
| Ref 2/ 4.7 E-Evaluation, Innovation and Research | - Commission and conduct work to measure and monitor effectiveness of strategic engagement activities. Focus on reputation and strategic direction. Include repeat of Focus Groups and Stakeholder interviews carried out by Consultation Institute. | Key stakeholders in NHS Wales, Welsh Government as identified in Stakeholder Mapping External Independent (if appropriate) | Stakeholder sentiment survey; focus groups and one to one interviews Repeat of Focus Groups and Stakeholder interviews carried out by Consultation Institute | Chief Executive and Exec Director of Strategy / Engagement Lead External Partners | Year 2 Q4 (Jan-Mar) |
| Ref 4.8 E-Evaluation, Innovation and Research | - Identify any engagement activities related to publication of Research and Innovation Strategy. | Research and Innovation Community | Desk-top Direct email and meetings with leads Independent Members | Medical Director Research and Innovation Working Group |  |
| Ref 2/ 5.1 F-Stakeholder Management | - Conduct further stakeholder mapping for specific projects and assigning leads and resources. | Internal (Programme/ Project Leads) Partners in Projects | Meetings and small workshops Established Project Governance | Exec Director of Strategy / National Clinical Informatics Lead - Public | Year 2 Q2 (Jul-Sep) |
| Ref 2/ 5.2 F-Stakeholder Management | - Facilitate a review of stakeholder maps to assess whether interests and influences have changed and if so why. | As set out in Strategy | Email / SharePoint messages Workshop if necessary | Exec Director of Strategy / National Clinical Informatics Lead - Public | Year 2 Q3 (Oct-Dec) |
| Ref 2/ 5.3 F-Stakeholder Management | - Review existing meetings and forums to align with Stakeholder Action plan. | As reflected in Stakeholder maps | Meetings and small workshops | Exec Director of Strategy / Engagement Lead | Year 2 Q1 (Apr-Jun) |
| Ref 3/ 6.1 G-Knowledge Exchange | - Develop and facilitate national and international knowledge exchange for digital related health and care services. | Open + targeted |  | Exec Director of Strategy / Medical Director / Independent Members / Research and Innovation Working | Year 3 |
| Ref 2/ 7.1 H-Governance | - Ensure engagement considerations are built in from outset and scrutinised and change in approach communicated. | Authors of Board and Committee Papers | Test of change to embed engagement in board governance papers and business proposals | Chair, Board Secretary | Year 2 Q2 (Jul-Sep) |
| Ref 2/ 7.2 H-Governance | - Align Digital Health and Care Wales strategies with that of our partners (where appropriate) to collectively understand direction of travel. | NHS Wales organisations | One-to-one Strategy Events Board Development sessions | Director of Strategy Board NHS Wales Organisations Welsh Government | Year 2 In line with planning cycles |
| Ref 2/ 7.3 H-Governance | - Revise strategic engagement (priorities timing, and resources) once Digital Health and Care overarching strategy published. | Digital Health and Care Wales Board | Board Development Session | Chief Executive Executive Director of Digital Strategy (When appointed) | Year 2 Once published? |
| Ref 2/ 7.4 H-Governance | - Strengthen public involvement and engagement through governance structures (Groups, committees). | Digital Health and Care Wales Committees | Discussion at meetings | Chairs of Digital Health and Care Wales Committees Board Secretary National Clinical Informatics Lead – Public / Engagement Lead | Year 2 and 3 |
| Ref 3/ H-7.5 Governance | - Identify and procure any external support to strengthen strategic engagement. | Digital Health and Care Wales Board | Board Development Sessions | Chair, Chief Executive, Board Secretary | Year 3 |

To understand the context of the Draft Action Plan it should be considered in conjunction with the Engagement Strategy.

The methodology for carrying out stakeholder focus groups and interviews is set out in Appendix one of the Engagement Strategy document.