DIGITAL HEALTH AND CARE WALES

December 2021

2021 - 2030

DHCW Decarbonisation Strategic Delivery Plan

TABLE OF CONTENTS:

1.	Who We Are	3

1.1 Digital Health and Care Wales	3

1.2 Our People	3

1.3 Our Carbon Management	3

1.4 Seren Environmental Consulting Ltd	3

2.	Statement of Commitment	4

3.	The Climate Emergency and Decarbonisation Targets	5

3.1 Climate Emergency	5

3.2 Decarbonisation Targets	5

4.	Principles for Public Reporting	8

4.1 Using the Principles for the Welsh Net Zero reporting approach system	8

5.	Wellbeing of Future Generations Act	10

5.1 Wellbeing Objectives	10

6.	Measuring DHCW’s Carbon Footprint	11

6.1 DHCW and the NHS Wales Carbon Footprint	11

6.2 Organisational Boundary	11

6.3 Emission Footprint Boundary	11

6.4 DHCW’s Baseline Data	12

7.	DHCW Baseline Carbon Footprint 2019/20	13

7.1 Gross Emissions	13

7.2 Net Emissions	15

7.3 Buildings	15

7.4 Transport	19

7.5 Procurement	23

7.6 Home Working	24

7.7 Improvement and Revision Approach	27

8.	2025 and 2030 Emissions Targets	28

8.1 Assumptions	29

9.	Strategic Delivery Plan	30

9.1 NHS Wales Strategic Delivery Plan	30

9.2 Mobilisation	30

9.3 Improvement and Revision Approach	30

9.4 Decarbonisation Initiatives	31

10.	ROADMAP	41

10.1 NHS Wales approach	41

10.2 Roadmap Review and Revision	41

10.3 DHCW Roadmap	42

11.	Conclusions	46

12.	Glossary	47

13.	References	48

# Who We Are

## 1.1 Digital Health and Care Wales

Established in April 2021, we are the National Organisation building and designing digital services for NHS Wales.

We are a new Special Health Authority created to take forward the digital transformation needed for better health and care in Wales, making services more accessible and sustainable while supporting personal health and well-being. Building on recent digital investment, we have a leading role in delivering the national programmes needed for modern technology-enabled healthcare. These large-scale developments will make a significant difference to the people of Wales.

As a relatively new organisation, we have a bold and ambitious programme of integration and innovation that includes expansion of the digital patient record and the creation of a world-leading national data resource, improving the way data is collected, shared, and used.

Our key responsibilities are mobilising digital transformation and ensuring high quality care, expanding access to the Digital Health and Care Record, delivering high-quality digital services and enabling big data analysis for better outcomes.

In order to deliver the digital aims of Welsh Government and to ensure the very best digital solutions for the people of Wales, we work collaboratively with health and care professionals, patients and public, industry and academia.

Our Values reflect and complement the NHS Wales Core Principles and wider public services values; they are at the core of how we work, both within DHCW and in our interactions with others.

## 1.2 Our People

We are led by a Board made up of executive directors and independent members, which is our most senior decision-making body. At the time of writing, DHCW has 885 employees.

## 1.3 Our Carbon Management

The Estates and Compliance team are currently responsible for defining the approaches and leading on implementing the initiatives detailed within this Delivery Plan. Beyond that, the team also works to collate and maintain environmental performance data, produce environmental statistics and reports as necessary, analyse environmental performance data and improve environmental communications across the organisation.

However, Estates and Compliance cannot deliver our decarbonisation aims without the assistance of key stakeholders both within DHCW and external to it (particularly NWSSP). As we do not own any of our offices or data centres, engagement with our landlords is vital to making meaningful progress.

## 1.4 Seren Environmental Consulting Ltd

This report was prepared with the assistance of Seren Environmental Consulting Ltd, who were selected to collaborate with Digital Health and Care Wales in the development of its Decarbonisation Strategic Delivery Plan following a competitive procurement process.

Seren Environmental Consulting Ltd are a small environmental management consultancy based in Swansea and Cardiff. Operated since 2003 by its two Directors, Amanda Thorpe and Matt Hines, the consultancy provides environmental management audit and consultancy including ISO14001 and carbon strategy for a wide range of organisations in the public and private sector.

# Statement of Commitment

A Foreword by the Chief Executive, Helen Thomas

Members of the Senedd endorsed the Welsh Government’s declaration of a Climate Emergency in 2019. The NHS Wales Strategic Delivery Plan, which DHCW are fully committed to, responds to this declaration, and is aligned with Welsh Ministers goal of achieving a net zero public sector by 2030.

Following the COVID-19 pandemic, a clear and ambitious green recovery strategy will be crucial. The Digital Health and Care Wales (DHCW) Decarbonisation Strategic Delivery Plan has been developed to support the ambitions set out within the NHS Wales Decarbonisation Strategic Delivery Plan. The plan demonstrates how NHS Wales can contribute to the recovery and its commitment to the Wellbeing of Future Generations (Wales) Act 2015, which addresses long-term persistent challenges such as poverty, health inequity, and climate change.

We have made significant progress in decarbonising our estate in recent years; however, we recognise that there is more to be accomplished. This Delivery Plan allows us to take a fresh look at our building and energy needs, as well as procurement, travel, and other emissions sources. Some of these emissions are beyond our direct control; highlighting the challenge we have in working collaboratively to influence the decisions of others.

DHCW are in a unique position to contribute towards reducing carbon emissions across the wider NHS by providing and improving digital solutions across NHS Wales, such as those allowing for digital transfer and storing of information and solutions that allow for remote consultation.

In recognition that the nature of our business activities may have an environmental impact, we are fully committed to decreasing this impact across the scope of our operations and the services we deliver.

Becoming more environmentally aware, we are actively taking steps to measure and reduce our carbon footprint to improve sustainability at DHCW by implementing improvement opportunities, enhancing our communication, and placing a greater focus on how we procure goods and services.

While there are a number of activities that can aid us in lowering the amount of carbon emissions that we emit as an organisation, we believe they must be undertaken as part of a comprehensive plan to ensure a complete transformation.

Crucially, our strategy is underpinned by the belief that any steps taken must consider not only how to address generated carbon emissions, but also how we as an organisation can become carbon efficient.

Our positive actions have contributed to embedding a sustainable culture within our organisation, reducing our negative effect on the environment. We will continue to actively work towards achieving our targets in this immensely important area.

In conclusion, each individual at DHCW has a part to play in decarbonising our estate and the wider health service in accordance with prudent healthcare. The decisions you make as an individual, or as a member of the team, will contribute to lowering emissions and enhancing our environment.

Helen Thomas

Chief Executive

Digital Health and Care Wales

# The Climate Emergency and Decarbonisation Targets

## 3.1 Climate Emergency

We know with high confidence that climate change is happening today (Climate Change Committee, 2021) and is the result of greenhouse gas emissions caused by anthropogenic (human) activity. Impacts from climate change are being felt today and will continue to increase in the future. The rising global temperature will be increasingly widespread and will lead to wider changes to our weather. Additionally, many impacts of climate change are already being detected and reported.

Globally, the IPCC (Intergovernmental Panel on Climate Change) has identified a range of concerns for the future (IPCC, 2021), including:

- irreversible impacts – even at more moderate changes in global temperature, particularly for Arctic ecosystems and coral reefs.

- extreme weather events

- severe impacts on the world’s poorest and most vulnerable populations

- environmental and economic damage

- large-scale singular events (such as further sea level rises as major ice sheets melt over Greenland and Antarctica)

Specifically, in the UK, the UK Climate Change Committee, 2021 has stated:

- The chances of experiencing hot summers like in 2018 have doubled in recent decades and are now about 10-20% per year. This will rise to 50% by 2050.

- Sea levels have risen by 16cm since 1900 and will continue to rise for centuries due to time lags in the climate system.

The UK climate change risk assessment (CCRA) shows a range of risks to the UK under different future scenarios of climate change and provides estimates of the current and future level of risk from flooding and coastal change; water scarcity; extreme heat; wildfires and storms (Climate Change Committee, 2021). These hazards will have increasing impacts on the natural environment, people, and the economy within Wales in addition to the UK as a whole. At the same time, there could be some opportunities, including reduced energy demand in winter, and a growing adaptation services sector. It is likely that these risks and opportunities will become increasingly more prominent in the future. New risks could emerge, as global greenhouse gas emissions continue to rise.

The climate change risks can be limited by reducing greenhouse gas emissions (mitigation) and preparing for change (adaptation). It is accepted that action to limit future global greenhouse gas emissions will help restrict future changes in the climate system.

## 3.2 Decarbonisation Targets

### 3.2.1 Global Climate Targets

Climate change is clearly recognised as a global problem needing a global response to keep global warming to ‘well-below’ 2°C above pre-industrial levels, and ‘pursuing efforts’ to keep it below 1.5°C.  At the 26th session of the Conference of the Parties (COP 26) to the UNFCCC (United Nations Framework Convention on Climate Change) held in Glasgow (November 2021) a formal commitment was made by countries and companies across the world to secure global net zero carbon emissions by 2050 and to keep 1.5 degrees of warming within reach. Few who have followed developments at COP26 will be in doubt as to the magnitude of the challenge ahead. In Wales, the Welsh Government has set out its intent for the public sector:

### 3.2.2 Welsh Government - A Net Zero Public Sector by 2030

In 2019, the Welsh Government declared a Climate Emergency and launched ‘Prosperity for All: A Low Carbon Wales’, which set out the Welsh Government’s plan for decarbonisation in Wales (Welsh Government, 2019). Since then, Welsh Government has put in place binding legislation, strategies, and ambitions to drive carbon reduction activity in Wales. In particular, a Welsh Government Ministerial Ambition’ has been set to achieve a Net zero Public Sector by 2030, including the health sector and NHS Wales.

In March 2021, the Senedd passed a suite of regulations to increase Wales’ emissions targets from those originally set in 2018/19 and to set Carbon Budgets accordingly. These targets and carbon budgets are now set in law and are as follows:

- Carbon Budget 2 (2021-25): 37% average reduction (with 0% offset limit);

- Carbon Budget 3 (2026-30): 58% average reduction;

- 2050: at least 100% reduction (Net Zero)

In May 2021, The Welsh Government published its Welsh Public Sector Net Zero Carbon Reporting Guide (Welsh Government, 2021), which detailed the principles and priorities for the Welsh Public Sector Net Zero Carbon reporting approach (known as the Welsh Net Zero Reporting Approach). This Guide defines the operational and organisational scope and the data which public bodies in Wales will need to assemble in order to fulfil the reporting requirements. A Net Zero Carbon reporting spreadsheet for the public sector has also been published.

In October 2021, The Welsh Government published its All Wales Plan 2021-2025 (Working Together to Reach Net Zero) focusing on specific actions and expectations needed to meet its 2025 carbon emission reduction targets.

The All Wales Plan specifically identified that a 7% carbon emission reduction by 2025 was needed from the public sector, as a whole, if Wales, as a whole, is to meet its collective net zero carbon targets by 2050.

The Welsh Government has established a ‘Team Wales’ approach, which means that there is an acknowledgement that different parts of the public sector will be able to make greater or lesser contributions to the net zero carbon reduction programme and that opportunities from carbon sequestration by NRW (Natural Resource Wales) managed woodland could also be legitimately included to offset those residual emissions that are difficult to eliminate (Welsh Government, 2021).

This is the reason that NHS Wales and DHCW do not themselves have absolute net zero targets by 2030. With this collaborative approach, the emissions from NHS Wales are included with all (780+) public sector organisations, including NRW and its woodlands. However, as NHS Wales has been identified as the biggest carbon emissions emitters, and potentially, one of the more challenging organisations to decarbonise, particularly against a potential increasing demand for health and care services, NHS Wales has to meet its share of the collective public sector target.

### 3.2.3 NHS Wales - 1 Million tonnes

As the largest partner in the public sector, NHS Wales has recognised it has a significant contribution to make towards the ‘Team Wales’ target of a net zero public sector by 2030.

The NHS Wales 2018/19 Carbon Footprint (Carbon Trust, 2020) was calculated to be approximately 1 million tonnes CO2e, which represents around 2.6% of Wales’s total greenhouse gas emissions. This has been set as the baseline for emissions reduction targets for NHS Wales going forward. Boundaries for scope 3 emissions have been defined (GP surgeries, pharmacies and dentists are a notable exclusion) and the future approach for NHS Wales has been established.

The NHS Baseline identified four key source areas for its carbon emissions, and their relative contributions to the 1 million tonnes of carbon emissions:

- Building Use (21%)

- Procurement (62%)

- Fleet & Business Travel (15%)

- Staff, Patient & Visitor Travel (2%)

These four categories are replicated in the NHS Wales Decarbonisation Strategic Delivery Plan, which was published in March 2021 (NWSSP) (Carbon Trust, 2021). The 2021 Decarbonisation Strategic Delivery Plan defined how NHS Wales intends to contribute towards a net zero Public Sector by 2030 by establishing 46 initiatives for decarbonising NHS Wales.

The NHS Wales Decarbonisation Strategic Delivery Plan has set the following headline targets:

- 16% reduction in carbon emissions by 2025

- 34% reduction in carbon emissions by 2030

### 3.2.4 Digital Health and Care Wales

DHCW recognise the Climate Emergency and the need for all those in the public sector to contribute to the ambitious net zero carbon by 2050 goal for Wales set by Welsh Government. All NHS organisations are expected to cascade the NHS Wales Decarbonisation Strategic Delivery Plan across their organisations and to develop and publish their own actions plans to demonstrate how initiatives within the plan will be delivered. This is our Plan.

In this Delivery Plan, Digital Health and Care Wales has:

- Outlined the decarbonisation challenge for our organisation

- Stated our commitments

- Estimated its baseline emissions using Welsh Government methodologies

- Identified priority sources of carbon emissions

- Established targets in line with those of NHS Wales (which in turn are aligned to the collective public sector ambition of being net zero by 2030)

- Shared the challenge that is particularly associated with procurement related carbon emissions

- Defined a mechanism for monitoring progress

- Adopted those initiatives within the NHS Wales Decarbonisation Strategic Delivery Plan that are relevant to DHCW

- Developed a roadmap of commitments and specific actions up to 2030 (which will be reviewed in 2025 and 2030) by which it will achieve its carbon reduction targets for 2025 and 2030.

We have established targets in line with those set by NHS Wales (which in turn are aligned to the collective public sector ambition of being carbon neutral by 2030) for our non-procurement emissions. These are:

- 16% reduction in carbon emissions by 2025

- 34% reduction in carbon emissions by 2030

We are developing our understanding of our significant procurement emissions in order to set a clear path to the 2025 and 2030 numerical targets. We intend to work with our colleagues at NHS Wales Shared Services Partnership (NWSSP) to define a clearer strategy in 2022.

# Principles for Public Reporting

## 4.1 Using the Principles for the Welsh Net Zero reporting approach system

The Welsh Net Zero reporting guide sets out thirteen principles to be adopted for public sector reporting. The principles are in order of priority and with the higher ranked principle expected to take precedence if there is conflict or uncertainty.

Digital Health and Care Wales have adopted these Principles when preparing the Baseline and Decarbonisation Strategic Delivery Plan.

| Principle name | Principle Adopted |
| --- | --- |
| 1. Transparency | Reporting has been transparent and has clearly stated the boundary, methods, data sources, uncertainty and assumptions used for estimation of emissions and removals. Areas of weakness or low-grade data have been highlighted. |
| 2. Good decision-making | DHCW will focus resources on accurately estimating and reporting on the most important activities. For DHCW, this is Procurement, followed by Building Use (particularly electricity consumption at the outsourced Data Centres), and then Business Fleet & Travel. |
| 3. Consistency | The methodology used to report emissions and removals has been applied consistently for 2019/20 and for subsequent prediction modelling. Changes reported between time periods will reflect actual changes to the quantity of emissions or removals, and not changes to the organisation or method. Outsourced activities will be accounted for to avoid carbon leakage. Clarification of scope definition with regards to procurement may be further defined and refined. This will be clearly reported. Confirmation of the rules for including/excluding examples where either DHCW occupies a small space (rooms or works stations) in another workplace and is not charged for the carbon impacts or vice versa, where another NHS team may sit within a DHCW workplace but is similarly not cross-charged for the carbon generated. |
| 4. Partnership working | DHCW understands that the 2030 ambition for the Welsh public sector can only be met by assessing carbon neutrality across the whole sector. Both NHS Wales and Digital Health and Care Wales have internal targets, independent of the overall Welsh public sector ambition and collaboration, partnership, open and honest communication and supportive networks will be critical to delivery of the Decarbonisation Strategic Delivery Plan. |
| 5. Usefulness of data | Our reported data reported will be directly useful for both measuring progress towards meeting the 2030 targets but also in understanding the risks and opportunities of targeted action. It is anticipated that our data will be of use to others within NHS Wales. |
| 6. Local Economic Growth | DHCW implements sustainable procurement and works hard to influence the wider economy through its demand for goods and services and its support for sustainable, low carbon economic growth. The carbon impact data generated and reported through this approach could support activities to develop and sustain low carbon markets in Wales and to provide evidence for supporting existing and potential future suppliers to those markets. |
| 7. Comparability | DHCW understands that the carbon neutral ambition for the Welsh public sector covers the whole sector and therefore it needs to report using the same operational and organisational boundaries, adjusted for organisation type, using the same standardised methodology and emission factors. Variations in boundaries and methodology based on organisational or geographical variation will always be clearly documented (in the case of the DHCW footprint versus that of NHS Wales 2018/19, the inclusion of home-working, necessitated by the profound changes to working patterns brought by the pandemic). |
| 8. Completeness | Reporting has included estimates for all emission sources within the agreed organisational and operational boundary, unless there is evidence to suggest that the emission source is not relevant for DHCW. For existing emission sources, where activity data was not available, DHCW has followed the provided methodology for estimating activity data, for example, benchmark estimates based on estate size or employee numbers. |
| 9. Proportionate reporting burden | The resources used to estimate emissions and removals have been proportionate to the significance of the source, firstly within NHS Wales, and secondly to DHCW. Whilst completeness and accuracy are important, DHCW has been mindful that it has to balance the need for robust estimates with the required resources. This means not devoting resource to reducing uncertainty for elements (such as waste and water) that form a very small component of the footprint. |
| 10. Improvement over time | DHCW’s data sets have some uncertainty. DHCW is therefore committed to improving the quality of reporting data over time, within the context of the overall reporting system. Methodologies will only be changed where this results in an improvement in terms of accuracy. There is an expectation that the methodology for assessing carbon data from procurement will evolve significantly over the reporting time period. Where DHCW has estimated emissions for significant source using simple approximations and benchmarks of activity data, DHCW will improve the methodologies in line with Principle 9. |
| 11. Accuracy | DHCW will reduce uncertainty in estimates of activity data and continually improve the accuracy of reporting, subject to Principle 9. Initial opportunities for this are identified later in this plan. |
| 12. Maintenance and extension of ambition | DHCW will commit to reducing all emissions further where possible and continue to search for new opportunities for carbon reductions. The boundaries of the reporting system may also be revised in the future to include emission sources outside the direct control and/or resetting of DHCW’s ambition to achieve net carbon removals. |
| 13. Peer review | To strengthen and share knowledge, DHCW is open to having its reported data peer reviewed by another NHS Wales reporting organisation. DHCW looks forward to participating in a peer learning community within NHS Wales. |

# Wellbeing of Future Generations Act

The Act came into effect in April 2016, which at the time made it the only piece of legislation of its kind in the world. It represents a significant opportunity for improving and changing life in Wales as a whole. The Act outlines how public bodies in Wales should collaborate to improve the economic, social, environmental, and cultural wellbeing of Wales.

In order to do this, we ensure as far as is practicable, that we deliver our work in accordance with the Sustainable Development principle; to act in a manner which seeks to ensure that the needs of the present are met without compromising the ability of future generations to meet their own needs.

The Act has established seven national wellbeing goals for Wales, illustrated below. We will contribute towards delivering these national goals through our Decarbonisation Strategic Delivery Plan, new ways of working and wellbeing objectives.

## 5.1 Wellbeing Objectives

A HEALTHIER WALES - Support the sharing of expert knowledge so that the citizens of Wales are better      informed about their health and able to access the best possible healthcare when they need it.

A GLOBALLY RESPONSIBLE WALES - Embed a sustainable culture to limit the impact on the environment.

A MORE EQUAL WALES - Attract, develop skills, and provide opportunities for existing and future generations.

A WALES OF COHESIVE COMMUNTITIES - Promote a culture of volunteering, by creating the conditions for citizens to share their experience and to learn new skills

A WALES OF VIBRANT CULTURE AND THRIVING WELSH LANGUAGE - Actively promote the use of the Welsh Language.

A PROSPEROUS WALES - Work to strengthen the international recognition of NHS Wales as a Centre of Excellence for Digital Innovation.

A MORE RESILIENT WALES - Improve the health and well-being of citizens across Wales, helping to sustain a healthy productive population that contributes to society.

# Measuring DHCW’s Carbon Footprint

## 6.1 DHCW and the NHS Wales Carbon Footprint

DHCW did not exist as an entity when the NHS Wales Carbon Footprint 2018/19 was calculated. At the time, its predecessor, the NHS Wales Informatics Services (NWIS) operated from within Velindre University NHS Trust. The NHS Wales carbon footprint (1,001,378 tCO2e) included NWIS (along with NWSSP and the Welsh Blood Service) within the ‘Footprint Boundary’, under the collective Velindre University NHS Trust footprint.

Other entities within NHS Wales have been able to use the NHS Wales Carbon Footprint 2018/19 in formulating their response to the NHS Wales Decarbonisation Strategic Delivery Plan. However, DHCW is unable to do so, without first estimating its own baseline emissions. Accordingly, DHCW has selected the subsequent year (2019/20) as its baseline year and estimated its own carbon footprint in that year. The rationale for 2019/20 as a baseline was that it was the first full year of carbon data associated with DHCW’s building portfolio and business travel arrangements as a separate organisation. At the time of writing, most data for 2020/21 was also available; however, this period was not suitably representative, dominated as it has been by the pandemic. In the discussion of DHCW’s 2019/20 baseline emissions, reference is made to preliminary 2020/21 data where it is useful for context and contrast.

## 6.2 Organisational Boundary

For the purposes of this Carbon Footprint, DHCW as an entity forms the organisational Footprint Boundary.

## 6.3 Emission Footprint Boundary

In common with the NHS Wales Carbon Footprint 2018/19, the operational boundaries are set using the Scope 1-3 Framework established by the Green House Gas Protocol (GHG Protocol, 2004).

NHS Wales Carbon Footprint Boundary (Carbon Trust, 2020)

The footprint boundary follows that of the NHS Wales footprint; the majority of emission types considered outside of the Footprint Boundary (shown in above image in grey) are ‘Scope 3 Downstream’ emissions. This is largely due to the lack of products downstream from NHS Wales; the nature of the organisation is such that there are no ‘sold products’. (Carbon Trust, 2020)

## 6.4 DHCW’s Baseline Data

The scope 1 and 2 carbon emissions associated with our building use and business travel have been monitored since 2019/20, by the Estates and Compliance team within DHCW, as part of its longstanding environmental management system (certified to ISO 14001:2015) which is independently audited each year. As our carbon, accounting has improved, so has the robustness and increased inclusivity of the Estates led data.

Through our ISO 14001 EMS, DHCW has put monitoring protocols in place to collate and analyse resource consumption and environmental data, much of it relevant to its carbon footprint. DHCW has developed a carbon accounting tool, based on UK Government published carbon factors to monitor its greenhouse gas emissions. The range of data currently collected includes:

- Electricity consumption

- Gas consumption

- Water (Supply & Treatment)

- General Waste Landfill

- General Waste WtE (Waste-to-Energy)

- Recyclable Waste (including confidential waste)

- WEEE (E-Waste)

- Business Mileage

- Fleet Vehicles

- Fleet Vehicles (Electric Vehicle (EV))

- F-Gas

- Procurement

Data availability, data quality, calculation methodologies and opportunities for reducing uncertainty are discussed against each type of carbon emission in the next chapter. Some very significant opportunities for reducing uncertainty exist. However, a baseline year of 2019/20 has been established, which is the first full year of carbon data associated with our building portfolio and business travel arrangements as part of being a separate organisation. Our emissions are subdivided into the four categories used by NHS Wales as follows:

- Building Use

- Procurement

- Fleet & Business Travel

- Staff Travel

When analysing and reporting on the data, NHS Wales aggregates the fleet and business travel with staff travel under the general headline of Transport.

For the purpose of carbon accounting, we include our outsourced Data Centres as part of the Building Use category rather than under a procurement classification. In the baseline year, DHCW’s own servers occupied rack space in two data centres. Although DHCW have no direct control over elements of data centre operation (e.g. cooling, considered under Scope 3 emissions), the servers themselves are owned and managed by DHCW and therefore emissions are considered as Scope 2 rather than Scope 3 emissions. Our rationale is simply that if a building includes our people or our equipment, then it makes sense for that building to be included in the footprint.

In addition, we have chosen to report estimated emissions from home working. These are small for 2019/20 but projected to be much larger in subsequent years. While this sets up a potential conflict with the NHS Wales baseline footprint (which excludes homeworking) under Principle 7 Comparability, we feel it meets the higher-ranking Principle 2 Good Decision Making. Moreover, recent approaches to carbon footprinting in Wales have begun to include homeworking, for example a case study by Natural Resources Wales (Welsh Government, 2021).

# DHCW Baseline Carbon Footprint 2019/20

## 7.1 Gross Emissions

The DHCW 2019/20 Gross Carbon Footprint has been calculated at 19,858 tCO2e.

This is about 2% of the NHS Wales 2018/19 baseline Carbon Footprint (1,001,378 tCO2e) and places it among the smaller entities within NHS Wales; similar to Public Health Wales but less than Powys Teaching Health Board (Carbon Trust, 2020). In the following sections, the overall footprint is broken down in various ways to aid understanding and in comparison with the NHS Wales footprint as a whole. Initially it is broken down Scope by Scope as set out in the GHG protocols:

Scope 1: Emissions from activities owned or controlled by the organisation that release emissions into the atmosphere. They are direct emissions. Examples of scope 1 emissions include emissions from combustion in owned or controlled boilers, furnaces, vehicles; emissions from chemical production in owned or controlled process equipment.

Scope 2: Emissions released into the atmosphere associated with the organisation’s consumption of purchased electricity, heat, steam, and cooling. These indirect emissions are a consequence of the organisation’s activities but which occur at sources that the organisation does not own or control.

Scope 3: Emissions that are a consequence of the organisation’s actions, which occur at sources that it does not own or control and which are not classed as scope 2 emissions. Examples of scope 3 emissions are business travel by means not owned or controlled by the organisation (staff using personal cars for work travel), waste disposal which is not owned or controlled, or purchased materials or fuels and energy consumption at outsourced Data Centres. (HM Government, 2019). This also includes those emissions associated with remote working.

Examples specific to DHCW’s footprint are:

Scope 1: exhaust emissions from DHCW fleet vehicles.

Scope 2: power generation emissions to provide electricity consumed at DHCW’s offices.

Scope 3: emissions in the production of IT equipment procured by DHCW.

NHS Wales’ carbon footprint is dominated by Scope 3 emissions. This is even more so for DHCW’s footprint, with Scope 3 Procurement emissions representing over 86% of the footprint. These emissions also have some data uncertainties due both to the methodology used and the data set available.

Of the remaining 14% of DHCW’s footprint, scope 2 emissions are the next largest source with scope 1 emissions being the smallest contributor.

In the NHS Wales 2018/19 Carbon Footprint report, emissions were broken down into three main categories; building use, transport, and procurement. The DHCW footprint adds Homeworking, as shown in the following summary table:

| Broad Category | Category | Scope | Emissions (T CO2e) | % |
| --- | --- | --- | --- | --- |
| Building Use | Natural Gas | 1 & 3 | 92 |  |
|  | Electricity (Offices) | 2 & 3 | 400 |  |
|  | Water & Waste | 3 | 10 |  |
|  | Electricity (Datacentres) | 2 & 3 | 1,109 |  |
|  | Subtotal |  | 1,611 | 8% |
| Procurement |  | 3 | 17,207 | 87% |
| Transport | Business Travel | 3 | 138 |  |
|  | Fleet | 1 | 22 |  |
|  | Subtotal |  | 160 | 1% |
| Staff | Commuting | 3 | 871 |  |
|  | Home Working | 3 | 9 |  |
|  | Subtotal |  | 880 | 4% |
| Total |  |  | 19,858 | 100% |

Table 1: Summary of DHCW’s baseline 2019/20 emissions by scope

The following figures contrast the relative importance of the categories in the NHS Wales (Carbon Trust, 2020) and DHCW footprints.

## 7.2 Net Emissions

The NHS Wales 2018/19 Carbon Footprint report follows the GHG Protocol and UK Environmental Reporting Guidelines in making a dual report to reflect ‘Net Emissions’. This report does likewise.

DHCW’s 2019/20 Net Emissions were 19,652 T CO2e.

NHS Wales’ energy procurement policy has moved to the purchase of REGO certified renewable electricity, and over half of DHCW’s electrical consumption is covered by REGO certification. This is consumption at Tŷ Glan-yr-Afon, Cardiff and Bocam Park, Pencoed.

REGO certificates are issued by OFGEM (Office of Gas and Electricity Markets) to generators of renewable electricity. Certificates can be used by licensed electricity suppliers to prove to the final customer that the energy was produced from renewable sources (i.e. off-site renewable generation). However, REGO certified renewable electricity is included when UK Government determines the overall carbon intensity of UK grid electricity, in order to calculate emission factors. DHCW uses these emission factors when calculating emissions relating to its electricity consumption, including that not covered by REGO certification. As there is the clear potential for double-counting the renewables component, REGO certificated electricity is not permitted to be used by public bodies as an offset reduction within the reportable Carbon Footprint.

For the purpose (only) of Net Emissions, REGO certified electricity is considered as zero carbon for generation (Scope 2) and associated ‘well-to-tank’ (Scope 3), but not for the associated transmission and distribution of the electricity (Scope 3).

In 2019/20, one of the two data centres used by DHCW reported use of 100% renewables, but certification details were not available at the time of writing. If REGO Certification were proven, the Baseline Net Emissions would be revised to 19,247 T CO2e.

## 7.3 Buildings

### 7.3.1 Introduction

DHCW currently occupy approx. 6,500 m2 of office floor space in a diverse range of buildings, under different landlords.

DHCW has a portfolio of six leased offices across Wales. These are:

Cardiff: Tŷ Glan-yr-Afon, 21 Cowbridge Road East (TGA)

Cardiff: Castlebridge 2, Cowbridge Road East (CB2)

Mold: Media Point – Unit 3, Mold Business Park (MMP) – occupied 2021

Pencoed: Bocam Park (Bocam Park)

Pontypool: Mamhilad House, Mamhilad Park Estate (Mamhilad)

Swansea: Technium 2, Swansea Waterfront Innovation Quarter (Technium)

- DHCW also has a small presence at the National Imaging Academy in Pencoed. All our leased offices sit within a wider healthcare, university, or commercial campus. We have no associated land or grounds with the lease arrangements. Our leased space varies from whole buildings to a few floors.

In addition to our offices, DHCW delivers services to NHS Wales from owned servers located at two third-party datacentres. During the footprint year, these were located in Blaenavon and Newport. In 2021, we closed our activities at Blaenavon and moved to a new Data Centre in Rhondda Cynon Taf.

### 7.3.2 Gas

#### 7.3.2.1 Introduction

Natural gas is largely non-renewable (a small percentage of UK grid gas is biomethane) and there are significant Scope 3 emissions associated with production and shrinkage (losses) during transmission. Natural gas is used for heating and hot water across most of DHCW’s buildings. Bocam Park and MMP do not have gas heating.

#### 7.3.2.2 Footprint Summary

Natural gas related emissions accounted for 92 TCO2e, which is just under 6% of the calculated Building emissions.

#### 7.3.2.3 Footprint Methodology

Emissions were estimated based on the methodology recommended by Welsh Government (Welsh Government, 2021) for TGA and Mamhilad, where gas meter information was available. Our gas consumption at Castlebridge, Technium and our previous North Wales office is estimated rather than metered because the landlord has apportioned our share of a communal heating system based on the amount of space we occupy.

#### 7.3.2.4 Reducing uncertainty for current methodology

There are no actions identified to further reduce the uncertainty of the emissions methodology.

### 7.3.3 Electricity (Buildings)

#### 7.3.3.1 Introduction

Use of electricity results in Scope 2 and Scope 3 emissions. Use of electricity in our buildings and datacentres is a significant element of our building carbon footprint.

We currently procure renewable electricity for half of our workplace offices, including our largest office (as do the owners of the Data Centres). This carbon footprint report follows UK Government carbon accounting rules (HM Government, 2019), which stipulate that this renewable electricity must not be rated as zero emissions (see ‘Net Emissions’ 7.2) but that the normal grid electricity carbon factor be used.

#### 7.3.3.2 Footprint Summary

Electricity-related emissions accounted for 400T CO2e, which is 25% of the calculated Building emissions.

#### 7.3.3.3 Footprint Methodology

Emissions were estimated based on the methodology recommended by Welsh Government (Welsh Government, 2021), using metered data for all sites except our previous North Wales office, where an estimate of consumption is based on floor area.

#### 7.3.3.4 Reducing uncertainty for current methodology

DHCW will investigate sub-metering at MMP.

### 7.3.4 Electricity (Datacentres)

#### 7.3.4.1 Introduction

In the baseline year, DHCW was using two major third-party data centres to locate and operate its equipment, at Blaenavon and Newport, in order to deliver its services to the rest of NHS Wales.

Data centres are major users of energy. The energy efficiency of datacentres is measured using industry benchmarks including:

- PUE (power usage effectiveness), which divides the amount of power coming into a data centre by the amount of power used to run data centre information technology equipment (cooling systems, UPSs, etc.).

- SUE (server usage effectiveness), which is a complement to PUE but also takes IT equipment efficiency into account when calculating data centre energy efficiency.

- DCIE (Data Centre Infrastructure Efficiency), which is expressed as a percentage calculated by dividing IT equipment power by total facility power.

While it has its limitations, PUE is the most often quoted benchmark.

A Cloud Strategy has recently been developed. Cloud services are much easier to scale than traditional on-premises environments. In an on-premises environment, in order to scale an application, we would have had to purchase an additional server or storage. With cloud services however, there is also the ability to turn servers and storage down, often without interrupting service.

For DHCW, this means that if there is less consumption than anticipated when a service is first implemented in the cloud, then the servers and storage associated with the service can be scaled down as required. Periodically monitoring server utilisation can produce substantial savings, as well as helping to ensure that the service runs optimally.

#### 7.3.4.2 Footprint Summary

Carbon emissions for the two datacentres was calculated at 1,109 TCO2e, which is 68.5% of the calculated Building emissions.

#### 7.3.4.3 Footprint Methodology

For the Newport Datacentre, carbon emissions relating to rack space power consumption were calculated based on the methodology for deriving carbon emissions from electrical consumption recommended by Welsh Government (Welsh Government, 2021), using monthly meter reads provided by the Data Centre.

No data was available for the Blaenavon datacentre, so on the basis that approximately the same amount of DHCW equipment was located at the two data centres, the Newport Datacentre metered consumption was adopted for the Blaenavon Datacentre.

The Scope 3 emissions around the wider operation of the datacentres (cooling loads etc.), apportioned to the DHCW equipment, were estimated using PUE’s. 2019 PUEs were not available for either datacentre. A PUE of 1.3 for Newport was based on an average ‘fleet’ PUE reported by the Data Centre for their range of datacentres. A PUE of 1.83 for Blaenavon was based on a UK & Ireland average from an EC study (Avgerinou, Bertoldi, & Castellazzi, 2017). These may be overestimates of real-world efficiency and should more information become available, an adjustment to the baseline will be straightforward.

Use of 100% renewable energy at Newport was not rated as zero, and instead, UK Grid emission factors were used.

#### 7.3.4.4 Reducing uncertainty for current methodology

A number of actions are identified:

- Obtain (and maintain) monthly meter data for data centres.

- Obtain (and maintain) PUE information from providers.

- Evaluate the robustness of reported PUEs, for example compliance with Green Grid comprehensive measurement standards or EU Code of Conduct for Energy Efficiency in Data Centres.

### 7.3.5 Water and Sewerage

#### 7.3.5.1 Introduction

Water requires treatment prior to supply and on its return to the environment. It is pumped and pressurised to reach end-users. All of these activities require energy and therefore result in greenhouse gas emissions. The water industry contributes 0.8 per cent of annual UK greenhouse gas emissions (Environment Agency, 2008). DHCW uses water for domestic purposes only (toilets and wash hand basins, drinking water, vending machines etc.). DHCW has no process uses of water.

#### 7.3.5.2 Footprint Summary

Water and sewerage related emissions accounted for 5T CO2e, which is 0.3% of the calculated Building emissions. The footprint does not justify actions on the basis of carbon emissions reduction. DHCW will however, continue to deploy best practical environmental management as part of its certified ISO 14001 programme and will continually improve to drive down all impacts associated with the water consumption in its offices.

#### 7.3.5.3 Footprint Methodology

Emissions were estimated based on the methodology recommended by Welsh Government (Welsh Government, 2021), where meter data is available. Where metered data is not available (at Castlebridge, Technium 2 and MMP), the calculated value for TGA was used, factored by gross floor area (Castlebridge, Technium and MMP are 13.5 times, 4 times and 3.4 times smaller respectively than TGA).

#### 7.3.5.4 Reducing uncertainty for current methodology

There are no actions identified to further reduce the uncertainty of the emissions methodology, due to the small contribution of water and sewerage to the total footprint.

### 7.3.6 Waste

#### 7.3.6.1 Introduction

Waste management generates emissions from transportation to processing and final disposal, whether that be to landfill sites, waste incineration or recycling sites. DHCW generates typical office type waste and waste electronic and electric equipment associated with its ICT activities. DHCW has a zero to landfill policy and has established waste minimisation and recycling programmes for all of its waste streams.

#### 7.3.6.2 Footprint Summary

Waste emissions accounted for 4.5 TCO2e, which is 0.28% of the calculated Building emissions. The footprint does not justify actions on the basis of carbon emissions reduction. DHCW will however, continue to deploy best practical environmental management as part of its certified ISO 14001 programme and will continually improve to drive down all impacts associated with waste in its offices.

#### 7.3.6.3 Footprint Methodology

Emissions were estimated based on the methodology recommended by Welsh Government (Welsh Government, 2021), using the relevant BEIS (Business, Energy, and Industrial Strategy) emissions factors, where tonnages were reported by the waste contractor. For some sites, a basic estimation was made based on the waste collection contract.

#### 7.3.6.4 Reducing uncertainty for current methodology

There are no actions identified to further reduce the uncertainty of the emissions methodology, due to the small contribution of water and sewerage to the total footprint.

## 7.4 Transport

### 7.4.1 Introduction

DHCW are a digital delivery service and its staff are required to travel to different NHS Wales primary and secondary care facilities, from GP Practices to hospitals, across Wales. Some activities can only be carried out physically on site. This could be an installation or troubleshooting type task but equally it could be to check equipment or interact with existing digital capability and work collaboratively with the local NHS team. During the pandemic, DHCW significantly reduced business travel by accelerating the ability to provide many digital services remotely. It is likely that this mode of remote service delivery will be sustained at a high level, but there will always be a residual requirement to travel which cannot be completely eliminated.

To a large extent, the geographical spread of the office network was to have staff local to all of the NHS Health Boards and Trusts, and therefore minimise both business and commuter travel.

### 7.4.2 Footprint Summary

Employee commuting was the largest element of transport emissions for NHS Wales, totalling 67% of the 165,000 TCO2e transport emissions (Carbon Trust, 2020). In DHCW’s baseline year, commuting was also the largest component, totalling 85% of the 1,031 TCO2e transport emissions. Staff commuting is a higher proportion of the DHCW footprint due to the absence of patient/visitor journeys, which form a major component of the NHS Wales transport footprint.

### 7.4.3 Fleet

#### 7.4.3.1 Introduction

DHCW operates a small fleet of vans (11), which are based across its Office locations and are used predominantly to transport IT equipment to and from NHS Wales locations. One electric van is used exclusively by the Estates and Compliance team for maintenance purposes.

#### 7.4.3.2 Footprint Summary

Fleet emissions accounted for 21.6 TCO2e, which is 2.1% of the calculated Transport emissions.

#### 7.4.3.3 Footprint Methodology

Emissions were estimated based on the methodology recommended by Welsh Government (Welsh Government, 2021), using fuel card data to gather information on litres of fuel consumed and calculate emissions using the appropriate fuel and WTT (Well-to-Tank) emission factors. Fleet vehicle data is acquired from Fuel Card reports. The quantity of fuel, in litres, is derived directly from the Fuel Card system reports.

#### 7.4.3.4 Reducing uncertainty for current methodology:

There are no actions identified to further reduce the uncertainty of the emissions methodology.

### 7.4.4 Business Travel

#### 7.4.4.1 Introduction

It has been straightforward to obtain data on our business journeys. This data has been collected for a number of years. However, it does not include any business journeys made by bus and train. These might currently be low in number and carbon impacts, but it is recognised that this is a data gap that we wish to address. With 96% of staff working remotely, business travel has been kept to a minimum.

#### 7.4.4.2 Footprint Summary

Business Travel emissions accounted for 138 TCO2e, which is 13.4% of the calculated Transport emissions.

#### 7.4.4.3 Footprint Methodology

Emissions were estimated based on the methodology recommended by Welsh Government (Welsh Government, 2021), using mileage data and calculate emissions using the appropriate fuel and WTT emission factors. Business mileage data is acquired directly from finance. The activity data is calculated by taking the cost claimed back by employees multiplied by 0.45p (standard mileage charge).

#### 7.4.4.4 Reducing uncertainty for current methodology:

Emission Factors for an average car of unknown fuel type was used. DHCW will consider options for capturing information on actual cars used.

### 7.4.5 Commuting

#### 7.4.5.1 Introduction

Commuting is travel between an employee’s home and place of work. Associated emissions are Scope 3 emissions, including direct emissions from the exhausts of workers’ road vehicles and emissions from public transport systems. Some organisations choose to place commuting outside of their carbon footprint reporting boundary. Welsh Government has chosen to include employee commuting in the Net Zero boundary, as did NHS Wales in their 2018-19 Carbon Footprint; DHCW have therefore included an estimate in our baseline. Welsh Government’s rationale is as follows:

Although, there are aspects of these journeys that are not under the full control of organisations e.g. the mode of transport and the commuting distance, organisations can influence it by:

› Availability of facilities promoting active travel such as secure bicycle parking facilities, showers and lockers

› Reducing availability of facilities promoting private travel such as employee parking

› Introducing working practices such as location flexibility so that employees can chose to work in an office closer to their residence

Therefore, during the stakeholder workshop, the Welsh Public Sector made a collective decision to include employee commuting in the Net Zero reporting boundary. (Welsh Government, 2021)

As discussed elsewhere in this report, the increase in remote working has reduced commuting emissions but increased emissions from power and heating in employees’ homes. The net movement in Scope 3 carbon emissions (and its scale) depends on a wide variety of factors, many of which vary over time.

#### 7.4.5.2 Footprint Summary

Commuting (Scope 3) emissions formed a significant part of DHCW’s operational carbon footprint and the methodology employed has a level of uncertainty.

DHCW commuting emissions have been estimated at 872 TCO2e for the 2019/20 baseline year (84.6% of the Transport emissions), based on 660 employees and 2% homeworking.

In 2020/21, homeworking reached an exceptional 96% in response to the pandemic and the estimated commuting emissions sank by over 95% to 40 TCO2e. There has also been a significant increase in staff numbers.

DHCW is unusual compared to the other organisational elements of NHS Wales. Most NHS Wales employees are, in large proportion, healthcare professionals and support staff who must travel to a healthcare facility such as one of the main hospitals or other places of employment to deliver their services to the public. A far greater proportion of DHCW’s workload can, and is, delivered remotely, provided sufficient planning and infrastructure are in place, meaning that total commute miles can be kept to a minimum.

Nevertheless, DHCW may also find opportunities to influence staff on their mode-of-transport choice.

#### 7.4.5.3 Footprint Methodology

Emissions were estimated based on the methodology recommended by Welsh Government, using average commuting distances, data from a publicly available study on the proportion of different modes of transport used by commuters in England and Wales (see table below); and emission factors for these modes.

Table 2: Commuting Modal Split (Welsh Government, 2021)

No travel survey has been conducted by DHCW at present and no DHCW-specific data on commuting distances or modes of transport was available. In the absence of this information, other data can be substituted, albeit with a higher degree of uncertainty. The result is a Tier 1 Methodology with a high level of uncertainty (Relative Standard Deviation (RSD) +/-25%). Data specific to DHCW was the headcount (as FTE) and the proportion of homeworkers.

According to the WG Carbon Reporting Guidance, the average commuting distance in Wales is 9.5 miles / 15.3 km, based on an RAC study (RAC Foundation, 2013). However, the NHS Wales 2018/19 Carbon Footprint Report estimates commute distance using information specific to NHS Wales staff. Staff commute distances were derived from payroll expenses data in which employee average distance from office to home is recorded. Staff travel survey data was also available for some Trusts, which gave commute distances and transport types.

For DHCW’s baseline, it was decided to use the mode of transport breakdown in the WG Carbon Reporting Guidance, along with an average of the commute round-trip journeys reported by the various Health Board/Trust travel surveys in the NHS Wales 2018/19 Carbon Footprint Report. NHS organisations that reported, calculated a round trip average varying between 15.56 and 29.39 miles. An average of 20.63 miles / 33.2 km has been derived for use by DHCW. UK Government (Dept for Business, Energy & Industrial Strategy, 2020) business travel Emission Factors for the relevant year were used.

For FTE (full-time equivalent) headcount, DHCW use the national Electronic Staff Record (ESR), which contains information, which is essential for effective workforce planning. The system has a range of tools and functions, which enable employers to enter, store and analyse historical and current information about the Workforce.

#### 7.4.5.4 Reducing uncertainty for current methodology:

The current footprint uncertainty can be reduced by gathering DHCW-specific information on commuting distances and modes of transport. DHCW will improve its approach from 2022 by carrying out a staff travel survey to gather this information.

## 7.5 Procurement

### 7.5.1 Introduction

DHCW purchase a wide variety of goods and services. Some of these purchases relate to our own needs and others (for example software licences) to the wider needs of NHS Wales. The annual spend is approximately £75M, when spend on staff pay is excluded. There is a close relationship with the NHS Wales Procurement Team – known as NHS Wales Shared Services Partnership (NWSSP).

The procurement spend of just under £75M (19/20) is substantial, but only around 4% of the NHS Wales ‘non-pay’ spend of £1,863m as reported in the 2018/19 carbon footprint report (Carbon Trust, 2020). DHCW’s procurement spend is likely to be similar in future years.

### 7.5.2 Footprint Summary

Procurement emissions accounted for 17,207 TCO2e, which is over 86% of the calculated DHCW 2019/20 Carbon Footprint. This compares with NHS-Wales’ 2018/19 Procurement footprint estimate of 62% of total emissions.

Procurement (Scope 3) emissions form by far the largest part of DHCW’s carbon footprint and the methodology employed has a high level of uncertainty.

### 7.5.3 Footprint Methodology

Basic information on DHCW’s procurement spend on goods and services was provided from the NHS financial management system. Emission estimates were based on the methodology recommended by Welsh Government  (Welsh Government, 2021).

The methodology simply multiplies the spend in pounds by an emission factor for the industry sector in which the spend was made. For example, £10M spend on computer equipment, using an Emission Factor of 0.41 for the SIC (Standard Industrial Classification) Code 26 computer, electronic and optical products, equates to scope 3 emissions of 4,107 TCO2e.

The Welsh Government methodology is assigned a Tier 1 (low) level of accuracy with a high level of uncertainty (RSD of +/-25%).

The method uses UK Government emissions factors derived in 2011, in the absence of more recent metrics. It should be understood that both the carbon intensity of some sectors and the purchasing power of sterling will have changed in the interim period.

- Overall, the purchasing power of sterling will have decreased since 2011.

- Overall, the all-sector average carbon intensity will have decreased since 2011.

In order to avoid double-counting of emissions with other parts of the calculated carbon footprint, some sub-categories of spend should be removed. For example, as DHCW have calculated business travel separately, expenditure on this category under SIC 49.3-5 Road Transport should not be included. However, the supporting information behind the broad categories available for the 2019/20 footprint did not allow these estimates to be made with any confidence in the time available and an unknown element of double-counting must therefore be assumed.

It should be noted that the NHS Wales 2018/19 footprint report (Carbon Trust, 2020) pre-dates the Welsh Government guidance and uses a related but rather more complex economic input-output analysis for procurement carbon emissions. This model uses more recent Emission Factor information and adjusts for currency purchasing power.

However, this method also follows the broad approach of spend against emission factor. Aside from accuracy, both methods are problematic, in that they cannot be used for target setting. For example, DHCW may target direct engagement of its major IT supplier leading to significant emission reductions, but the calculated footprint, correlating only to spend, would remain unaffected.

### 7.5.4 Reducing uncertainty for current methodology

The current footprint estimate is based on a basic review of summary information in a restricted timescale, most likely leading to inaccuracy beyond that envisaged by the methodology. In 2022, DHCW will improve its approach by the following measures:

- Clarify which procurement model is to be used by NHS Wales going forward.

- More detailed analysis of spend to:

- Better understand spend in categories with substantial spend and opaque descriptions e.g. 37470-Miscellaneous Expenditure and 37400-Other General Provisions.

- Assess whether the emission factors used for these categories were realistic

- Identify and strip out double-counting within DHCW’s own carbon footprint, for example relating to travel or building management.

- Identify and strip out double-counting with other NHS Wales bodies’ carbon footprints, for example where ICT equipment is procured for those bodies.

- Investigate and clarify the procurement Scope 3 emissions boundaries, where DHCW procure ICT equipment on behalf of other NHS Wales bodies.

- Separate capital and non-capital goods and services to align with GHG protocol and WG guidance.

- Use the output from this analysis to re-baseline the 2018/19 procurement carbon footprint.

- Set up an MoU or similar with DHCW Procurement and NWSSP on data provision and footprint allocation in future years.

- The Welsh Government guidance recommends their procurement methodology in the absence of freely available calculated product footprints for the majority of goods and services (Welsh Government, 2021). However, in ICT, calculated footprint information is becoming available. For example, DHCW are major users of one provider’s servers, laptops, and related products, for which carbon footprint information is available on a model-by-model basis. DHCW will investigate whether for some ICT procurement categories, emissions can be more accurately derived from manufacturers’ information rather than from crude emission factors.

## 7.6 Home Working

### 7.6.1 Introduction

Encouraging home working has the potential to reduce Scope 1 and 2 emissions from DHCW’s buildings; in the short term through reduced energy demand at existing offices, and in the medium term through opportunities to reduce the office portfolio. Home-working also reduces Scope 3 emissions relating to commuting, as less journeys have to be made.

However, home workers consume energy for office equipment, home heating and in some settings home cooling. These result in Scope 3 carbon emissions, which may not have occurred if the workers had been in the office.  Including the indirect, displaced scope 3 emissions from remote working in our baseline will allow meaningful comparisons with year-on-year performance to be undertaken, especially for 2020/21, which saw only 4% working in the office locations.

In order to properly account for these Scope 3 emissions, DHCW has applied a methodology developed by EcoAct, in partnership with Lloyds Banking Group and NatWest Group (Ecoact, 2020). The methodology evolved as a response to the huge increase in home-working due to the COVID-19 Pandemic, in which DHCW itself saw a successful migration to 96% homeworking. Considering the Welsh Government’s target for 30% remote working (Carbon Trust, 2021), the need to account for related emissions within DHCW’s carbon footprint is clear, to avoid over-reporting of savings.

The current version of Welsh Government carbon reporting guidance requires estimation of Scope 3 commuting emissions but not Scope 3 home-working emissions. Given the increasing importance of home-working, the latter must inevitably change and DHCW has made the decision to add it to their baseline year.  It is noted that NRW has already reported its working from home emissions (Welsh Government, 2021) and calculated both the impact of remote working during the pandemic and what this could mean for its future emissions if it were to operate at levels of 30% or 60% homeworking.

### 7.6.2 Footprint Summary

Using the EcoAct Base Case methodologies, a footprint of 9.4 TCO2e has been calculated for the 2019/20 baseline year, based on an average 2% home working, which was wholly due to pandemic lockdown in the last weeks of the period. Less than 10% of these emissions arise from use of office equipment and lighting; the remainder arise from home heating. In 2020/21 the huge increase in homeworking (estimated at 96% over the year) led to a >5000% increase to 515 TCO2e. However, there was a corresponding reduction in carbon emissions from business travel and commuting, and there was an overall net reduction of 500 tonnes. It should be noted that working remotely significantly reduced travel related carbon emissions, which are usually challenging to address (as well as reducing office building related emissions).

| Category | 2019/20 | 2020/21 |
| --- | --- | --- |
|  | Pre Pandemic TCO2e | During Pandemic TCO2e |
| Commuting | 871 | 40 |
| Homeworking | 9 | 515 |
| Business Travel | 138 | 6 |
| Total T CO2e | 1018 | 561 |

### 7.6.3 Methodology

As the Welsh Government carbon reporting guidance does not require estimation of Scope 3 homeworking emissions, it provides no methodology. Within the WG framework, the methodology adopted would be classed as a Tier 1 method with high uncertainty (RSD +/-25%).

For detail on the homeworking methodology adopted, the reader is referred to the EcoAct Homeworking Emissions Whitepaper (Ecoact, 2020). The methodology offers ‘Base Case’ and ‘Enhanced Case’ for Office equipment, Heating energy and Cooling energy. In the absence of additional data, DHCW have adopted the Base Case for office equipment, the Base Case for Heating Energy and have discounted Cooling energy as not significant in Wales during the baseline period. The method assumes (based on a 2020 NatWest Group staff survey (Ecoact, 2020)) that in approximately 1/3 of cases, there is another occupant present and no additional need for heat arises from home working.

DHCW-specific data used for the exercise were the average headcount as Full Time Equivalent (FTE) and the percentage home working. The latter was calculated by the small number of weeks at the end of the baseline year that offices were shut due to the pandemic.

### 7.6.3 Reducing uncertainty for current methodology

The current footprint estimate uses the EcoAct Base Case throughout. DHCW will transit from Base Case to Enhanced Case data wherever reasonable to do so, using EcoAct’s own recommendations as a starting point:

- Working Hours and Days:

- Adjust to DHCW specific contract hours and working days (considering annual leave allowance)

- Office Equipment Emissions:

- Collect internal records for standard issued equipment (laptop/tablet/screen), including number of devices and typical “in use” power consumption, or;

- Staff Survey to confirm typical equipment in use. Data from respondents apportioned across non-respondents

- Staff Survey to confirm typical lighting equipment in use. Data from respondents apportioned across non-respondents.

- Staff Survey to confirm proportion of colleagues purchasing Green energy at home. Used to support Market-Based reporting and/or the encouragement of green tariff take up.

- Heating Energy Emissions:

- Staff Survey to confirm typical home energy use and shared occupancy. Where shared occupancy arises and other occupants are “homeworking”, companies should report a proportional share of emissions. Where other parties are “stay at home” (e.g. stay at home parent/carer) companies can exclude heating emissions on account of zero increment. Data from respondents apportioned across non-respondents.

- Staff Survey to verify DHCW’s assumptions re. home cooling.

In addition, DHCW need to put in place a system to track the amount of working from home when its offices are back in normal operation.

## 7.7 Improvement and Revision Approach

Opportunities to improve accuracy and reduce uncertainty have been identified against each category of emission reported. As the 2020/21 Carbon Footprint is close to being finalised, DHCW will action these opportunities where possible, prior to collation of its 2021/22 Carbon Footprint. These activities are captured in the Roadmap (see Section 9). It is anticipated that some more straightforward opportunities could be realised in time for the 2020/21 Carbon Footprint.

Where it is possible to correct errors or significantly improve uncertainty, DHCW may revise the 2019/20 Baseline Carbon Footprint.

# 2025 and 2030 Emissions Targets

DHCW has mapped its emission decarbonisation pathway between 2019/20 and 2029/30. A ‘Business as Usual’ scenario has not been included because it is not a viable or intended option.

Note: There is an expected reduction in the carbon emissions for 2020/21 and 2021/22 due to the significant impacts of the COVID-19 pandemic. The graph has taken this into account, although the footprint for 20220/21 is yet to be finalised.

The Digital Health and Care Wales decarbonisation targets are set as follows:

Scope 1 and 2 Emissions (excluding Procurement data):

| DHCW Target | Emissions (T CO2e) | Percentage reduction from 2019/20 | Cumulative Savings from Initiatives will total T CO2e |
| --- | --- | --- | --- |
| Baseline | 2,651 | - | - |
| 2025 | 2,227 | -16% | 424 |
| 2030 | 1,750 | -34% | 901 |

Scope 1, 2 and 3 Emissions Total (including Procurement data):

| DHCW Target | Emissions (T CO2e) | Percentage reduction from 2019/20 | Cumulative Savings from Initiatives will total T CO2e |
| --- | --- | --- | --- |
| Baseline | 19,858 | - | - |
| 2025 | 16,681 | -16% | 3,177 |
| 2030 | 13,106 | -34% | 6,752 |

Note that the figures in the first and third tables do not match in 2025 and 2030 because one set are targets (tables 1 and 2) and the other (table 3) are predictions.

Our Delivery Plan is designed to achieve the NHS Wales 2025 and 2030 targets of 16% and 34% emissions reductions in our gross operational emissions. We have forecast our non-procurement ‘Operational’ emissions up to 2029/30 to predict the impact of our key actions in our Delivery Plan. For clarity,

- Third party Datacentres are included because (i) better data is available than procurement spend-based emissions factors, and (ii) we consider the emissions directly related to our equipment’s energy consumption to be Scope 2 (datacentre cooling etc. remains Scope 3).

- Home-working is included because, although very small in the baseline (660 FTE staff, with approx. 2% homeworking), we expect it to be an integral part of our operational arrangements going forward.

The plan to reduce procurement related emissions is being led by NWSSP through their own Delivery Plan.  However, with our digital expertise, we acknowledge that we have a major role to play in assisting NWSSP to identify realistic reduction pathways for procurement of IT Goods and Services. We will work with NWSSP in 2022 to scope out the way forward so that numeric reduction targets may be set for subsequent years.

| Non-Procurement Operational Emissions - 10 Year Predictions | 2019/20 | 2024/25 | 2029/30 |
| --- | --- | --- | --- |
| Office Buildings | 502 | 233 | 102 |
| Data Centres | 1,109 | 921 | 779 |
| Working Remotely | 9 | 166 | 145 |
| Transport | 1,031 | 762 | 690 |
| Total TCO2e | 2,651 | 2,083 | 1,716 |

Table 3: Baseline Emissions and Predictions for 2025 & 2030 for Operational Emissions (Office Buildings, Data centres, Transport & Working Remotely)

Our modelling of predicted carbon reductions from this Decarbonisation Strategic Delivery Plan gives a 21% reduction by 2025 and a 35% reduction by 2030. There is an element of cautiousness when carrying out the modelling. DHCW intends to review and report on its carbon footprint annually. This will then be the opportunity to assess performance against predicted carbon emissions. It is likely that individual years may vary up or below predictions but that the 2025 and 2030 targets are achievable by carrying out the proposed decarbonisation initiatives.

In carrying out the modelling, a number of technical assumptions have been made, and must be included, for reasons of transparency. These assumptions are as follows:

## 8.1 Assumptions

### 8.1.1 UK Grid Emission Factor

The UK Grid Emission Factor is forecast to fall significantly by 2030. This has been modelled into the office and homeworking electricity footprint. National Grid  have forecast the carbon intensity of the grid for the next 5 years and carried out modelling based on four grid carbon intensity 10-year scenarios’; ‘Steady Progression’; ‘System Transformation’; ‘Consumer Transformation’ and ‘Leading the Way’ (National Grid ESO, 2020). We have used the most conservative of those ‘Steady Progression’ to estimate annual grid emission factors for Indirect (Electricity) and WTT Electricity (Generation). The Emission factors for Transmission & Distribution – UK Electricity and WTT – UK electricity (T&D) have been kept at 2019 values.

### 8.1.2 Datacentre Footprint

Data requirements are expected to rise as the Digitalisation of NHS Wales continues, therefore we have developed a Cloud Strategy to define and communicate our unified strategy and direction on the adoption of cloud computing technologies and services. Cloud computing services are uniquely positioned to support our strategic technology requirements for the future. We will adopt cloud computing services using a cloud-first approach for both new and existing workloads by 2024. The efficiency of IT equipment is expected to rise. As discussed above, the UK Grid Emission Factor is expected to fall. For now, a working assumption is made that these competing factors will broadly cancel themselves out. This is a critical assumption with a high level of uncertainty; improvement in this area is a priority.

Other assumptions include:

### 8.1.3 Homeworking:

- Average home heating to become 5% less carbon intensive from 26/27, 10% from 29/30.

- Carbon awareness raising with staff will yield a 1% year-on-year reduction in home workers’ electricity-related emissions.

### 8.1.4 Commuting:

- National measures to reduce commuting carbon intensity will contribute at least 50% of the forecast footprint reductions.

### 8.1.5 Datacentres:

- Datacentres used will conform with the EU Code of Conduct on Data Centre Energy Efficiency (for example in PUE reporting), or national or ISO equivalent.

- There will be a move to a Cloud based approach over future years.

### 8.1.6 Office Lighting:

- 40% of baseline office electricity consumption is lighting.

- 10% of baseline office electricity consumption is LED lighting.

- On average, a 40% reduction in consumption is achieved per luminaire when change to LED.

# Strategic Delivery Plan

## 9.1 NHS Wales Strategic Delivery Plan

NHS Wales identified 46 Decarbonisation Initiatives, of which 20 were directly or indirectly applicable to Digital Wales. In producing their Decarbonisation Strategic Delivery Plan, NHS Wales provided a framework, which Health organisations could adopt to show compatibility, integration, and support. The DHCW Delivery Plan is deliberately adapted and co-ordinated with that of NHS Wales to demonstrate synergy.

## 9.2 Mobilisation

The success of this Delivery Plan will be highly dependent on the governance structure put in place at DHCW. As with NHS Wales, DHCW will have an ambitious management approach to ensure sustained momentum, and provide the financial investment put forward to support implementation.

The following activities set out the implementation approach for the Delivery Plan; these are split between mobilisation and an improvement approach. Further detail regarding the specific actions, responsibilities, and target dates are available.

- DHCW will always show leadership and commitment to deliver this Decarbonisation Strategic Delivery Plan in order to address the Climate Emergency for Wales as declared by Welsh Government and the Senedd.

- A ‘Decarbonisation Group’ will be put in place to oversee implementation of the Delivery Plan; this will include a wide range of interested parties from within DHCW.

- A ‘Decarbonisation Programme Manager’ will be put in place as a dedicated role to drive the focussed implementation of the Delivery Plan. Specifically, this will be managed by the Estates and Compliance Team.

- ‘Action Plans’ will be embedded into our existing ISO 14001:2015 environmental management system developed – these will be reviewed annually

- DHCW will enable the successful implementation of the Delivery Plan by supporting access to additional resource and finance for delivery of initiatives, using external resources and collaborating with NHS partners and third parties where necessary.

## 9.3 Improvement and Revision Approach

- Our Estates and Compliance Team will oversee the evolution of our monitoring and measurement processes to capture improved data coverage, reduce the level of uncertainty and communicate carbon performance – aligned with Welsh Government and NHS Wales reporting guidelines. - DHCW will actively support the work of NWSSP in the progression of procurement emission related carbon accounting.

- DHCW will issue a revision of this Delivery Plan with updated and refined targets by 2023. - DHCW will review the success of this Delivery Plan implementation in 2024 and issue an update on the Plan in 2025.

## 9.4 Decarbonisation Initiatives

NHS Wales lists six activity streams for which decarbonisation activities have been identified:

- Carbon Management

- Buildings

- Transport

- Procurement

- Estate Planning and Land Use

- Approach to Healthcare

Each activity has a subset of decarbonisation initiatives that DHCW must consider and implement if relevant to its activities. The following table summarises the NHS Wales initiatives and DHCW’s intentions, where they are relevant.

Note: In the below tables, initiatives (rows) greyed out are not applicable to DHCW.

### 9.4.1 Carbon Management

| No. | NHS Wales Initiative | DHCW Initiative |
| --- | --- | --- |
| 1 | Implement best practice carbon management with dedicated roles in place to undertake Delivery Plan initiatives. | DHCW has appointed the Estates and Compliance team to lead on the Decarbonisation Delivery, with support from key teams (and an external Consultant to assist with the development of the Plan). DHCW has a certified ISO 14001 environmental management programme through which it will plan, do, check and act upon all decarbonisation initiatives. |
| 2 | Proactively communicate the Climate Emergency to staff and the public with the aim of stimulating low carbon behaviours and growing engagement in the decarbonisation agenda. | DHCW actively uses digital noticeboards and TENtalks to raise awareness on all aspects of sustainability, including climate change, throughout the year. Dedicated sustainability and environmental management SharePoint pages are used to communicate the Decarbonisation Strategic Delivery Plan and our carbon footprint. |
| 3 | Drive the engagement required for decarbonisation across each organisation’s leadership teams to develop a focussed and active approach to project implementation. | DHCW has senior leadership involvement for all aspects for its environmental management and sustainability programmes. This is fully extended to include Decarbonisation of Digital Health and Care Wales. |

### 9.4.2 Buildings

| No. | NHS Wales Initiative | DHCW Initiative |
| --- | --- | --- |
| 4 | Progress a transformational energy and water efficiency retrofit programme across the estate – every building with a long-term future will have undergone a multi-technology energy-efficient upgrade by 2030. | DHCW leases all of its workspace from commercial organisations or other NHS Health Bodies. As part of refurbishment projects, prior to DHCW occupying two of our premises (MMP and CB2), we actively engaged with our landlords, to install efficient heating and cooling systems. DHCW commits to including Decarbonisation and energy efficiency upgrades of those buildings we occupy. This will be included as a central priority and obligation within our Estates Strategy and in our liaison and negotiations with the landlords. This includes both the office buildings and the Data Centres. We will adopt cloud computing services using a cloud-first approach for both new and existing workloads |
| 5 | Fully replace all existing lighting with LED lighting by 2025. | Whilst there has been a progressive rollout of LED lighting across our portfolio of office buildings, it is not yet 100%. DHCW will commit to installing 100% LED lights by 2025, if not sooner. |
| 6 | Complete expert heat studies by the end of 2023 for all acute hospitals to set the plan to transition away from fossil fuel heat sources | Initiative relates to conducting Heat Studies in hospitals and is therefore not applicable to DHCW. |
| 7 | Progress low carbon heat generation for all non-acute sites larger than 1,000m2 by 2030. | DHCW currently has workspace in one building that is larger than 1000m2 (Tŷ Glan-yr-Afon). This building is leased to DHCW only; however, a section of the building is separated from DHCW occupied areas and houses local residents. The building uses natural gas for heating purposes. Gas consumption is monitored. DHCW will work with its landlord to seek low carbon alternatives to using natural gas for heating at TGA. |
| 8 | We will not plan to install any further natural gas CHP plant - renewable CHP will be championed instead. For existing CHP plant, we will prioritise decommissioning over investment in major refurbishment of failed CHP from 2025, with the ambition for all CHP to be decommissioned by 2030. | DHCW does not have any natural gas CHP on its office or data centre sites and has no intention of installing natural gas CHP in the future, therefore this initiative is not applicable to DHCW. |
| 9 | Take an active approach to efficient control of energy in buildings. All buildings will have up-to-date, standardised, and effective building management systems (BMS). Dedicated resource to optimise the use of energy by BMS control will be put in place by 2023. | DHCW commits to taking an active approach to efficient control of energy in our buildings, using our certified ISO 14001 EMS. DHCW Estates and Compliance team will work with all its landlords to achieve up-to-date, standardised, and effective BMSs by 2023. DHCW commits to taking an active approach to improve efficiency, the refurbishment and upgrading of building technology, including BMS, is part of our ongoing Estates Strategy and scope for future BMS improvements have been identified. DHCW currently has workspace in six buildings that are leased either from commercial organisations or Health Boards and rack space in two commercial Data Centres. Energy efficiency in the data centres we use is a key performance indicator both in the procurement process and in ongoing operational relationships. |
| 10 | Determine the overall viable potential for onsite renewable energy generation at each NHS Wales organisation by 2023. Install half of this potential by 2026, and the remainder by 2030 | Due to the nature of our building leases, there are currently no onsite renewable energy opportunities for DHCW at its office buildings. This is therefore determined to be zero at this time. There are solar panels installed on one of the commercial data centres and panels are about to be installed on the other Data Centre but these properties are not owned by DHCW. |

### 9.4.3 New Builds and Major Refurbishments

| No. | NHS Wales Initiative | DHCW Initiative |
| --- | --- | --- |
| 11 | Develop and build low carbon buildings to net zero standard – engage and collaborate with NHS partners across the UK on the emerging net zero building standard for hospitals and adopt a net zero building accreditation approach which will be defined by 2022. | DHCW does not carry out construction or major refurbishment of buildings. In general, all refurbishments are internal and interior modifications of the workspaces. At this moment, initiatives relating to New Builds and Major refurbishment are not directly applicable. Should this ever change, then DHCW is committed to implementing these Initiatives also. |
| 12 | All project teams to have an independent client-side sustainability representative to provide due diligence support for the optimal low carbon design across all development stages – and be responsible for ensuring the Net Zero Framework process is followed. | DHCW has appointed the Estates Team to provide sustainability guidance on building leases and refurbishments and support the Net Zero Framework. Sustainability will be considered as part of all future projects. |
| 13 | Integrate Modern Methods of Construction (MMC) into the design and construction of new buildings – this will consider modular design, offsite fabrication, and just-in-time delivery to minimise construction-related carbon emissions | DHCW does not carry out construction or major refurbishment of buildings. In general, all refurbishments are internal and interior modifications of the workspaces. At this moment, Initiatives relating to New Builds and Major refurbishment are not directly applicable. Should this ever change, then DHCW is committed to implementing these Initiatives also. |
| 14 | Install electric vehicle charging points in new developments beyond minimum requirements, and future-proof new car parks by installing infrastructure to enable straightforward installation of future charging points. | DHCW installed 4 electric vehicle charging points at Tŷ Glan-yr-Afon in 2017/18 and a further 4 more in 2020/21 at Media Point. Plans are in place to install an additional 4 EV charging points at TGA in 2021/22. DHCW is committed to working with its landlords to install additional EV charging points. |
| 15 | Prioritise low carbon heating solutions as a key design principle. No fossil fuel combustion systems are to be installed as the primary heat source for new developments. | DHCW has a mixed portfolio of offices and the associated heating arrangements are diverse. Opportunity was taken at the new office, Media Point, Mold to switch away from using natural gas as the means of heating (and to purchase a renewable electricity tariff). DHCW is committed to working with its landlords to prioritise low carbon heating and will not install fossil fuel heating as the primary heat source in any new office building. |
| 16 | Incorporate the principles of sustainable transportation into the design of new sites (in addition to electric vehicle infrastructure) in line with the Welsh Government’s Active Travel Action Plan for Wales | DHCW does not carry out construction or major refurbishment of buildings. In general, all refurbishments are internal and interior modifications of the workspaces. At this moment, initiatives relating to New Builds and Major refurbishment are not directly applicable. Should this ever change, then DHCW is committed to implementing these Initiatives also. |

### 9.4.4 Transportation

| No. | NHS Wales Initiative | DHCW Initiative |
| --- | --- | --- |
| 17 | NWSSP will work with Health Boards and Trusts to develop the best practice approach for electric vehicle (EV) charging technology, procurement, and car park space planning – this will include consideration of NHS Wales’ own fleet, staff vehicles, and visitor EV charging. | DHCW will work with all NHS organisations, including NWSSP with regards to electric vehicle (EV) charging technology, procurement, and car space planning. DHCW has already started installing EV charging points. |
| 18 | A standardised system of vehicle management for owned and leased vehicles will be developed to plan, manage, and assess vehicle performance - this will entail central fleet management oversight within each organisation. | DHCW will participate in any NHS standardised centralised system of vehicle management for owned and leased vehicles. |
| 19 | All new cars and light goods fleet vehicles procured across NHS Wales after April 2022 will be battery-electric wherever practically possible. In justifiable instances where this not suitable, ultra-low emission vehicles should be procured. | DHCW does not procure vehicles. Instead, DHCW has a policy of leasing vehicles for staff business use through the NWSSP All Wales Lease Scheme. |
| 20 | All new medium and large freight vehicles procured across NHS Wales after April 2025 will meet the future modern standard of ultra-low emission vehicles in their class. | Initiative relates to the procurement of large freight vehicles and is therefore not applicable to DHCW. |
| 21 | All Health Boards and Trusts will appraise the use of staff vehicles for business travel alongside existing pool cars. Health Boards and Trusts will update their business travel policies to prioritise the use of electric pool cars, electric private vehicles, and public transport. | DHCW is committed to decarbonising its vehicle travel and will work with other Health Boards and Trusts to increase the availability of electric charging points to facilitate staff use of electric cars and vans. DHCW provided public travel alternatives as an option (Rail via Transport for Wales and Cardiff First bus) to all our staff. DHCW has a documented Travel Plan. We will carry out a travel survey and review the use of staff vehicles for business travel alongside the use of lease cars. |
| 22 | The Welsh Ambulance Service NHS Trust will continue to develop their electric vehicle charging infrastructure network plan for the existing NHS Wales estate to facilitate the roll-out of electric vehicles. | Initiative relates to the Welsh Ambulance Service NHS Trust and is therefore not applicable to DHCW. |
| 23 | The Welsh Ambulance Service NHS Trust will aim for all rapid response vehicles procured after 2022 to be at least plug-in hybrid EV, or fully battery-electric in appropriate locations. | Initiative relates to the Welsh Ambulance Service NHS Trust and is therefore not applicable to DHCW. |
| 24 | The Welsh Ambulance Service NHS Trust will actively engage with vehicle manufacturers for research and development of low carbon emergency response vehicles and report annually, with the ambition to operate plug-in electric, or alternative low carbon fuelled, emergency ambulances by 2028. | Initiative relates to the Welsh Ambulance Service NHS Trust and is therefore not applicable to DHCW. |

### 9.4.5 Procurement

| No. | NHS Wales Initiative | DHCW Initiative |
| --- | --- | --- |
| 25 | NWSSP will transition to a market-based approach for supply chain emissions accounting. | Currently, Digital Health and Care Wales is using the supply chain emissions tool provided by Welsh Government for use in the public sector. It is anticipated that the method of carbon accounting for procurement emissions will evolve. DHCW believes its specific type of digital and ICT goods and services are well suited to early adoption of more refined accounting tools. |
| 26 | NWSSP will expand its current Sustainable Procurement Code of Practice to include a framework for assessing the sustainability credentials of suppliers. | DHCW purchases goods and services directly. It also uses the services of NWSSP. Both organisations follow the Sustainable Procurement Codes of Practice for all purchased goods and services, regardless of which organisation takes the lead Buying role. |
| 27 | Value to the local supply chain will be maximised, whilst maintaining high standards for goods and services. | DHCW has established protocols for increasing the amount of goods and services purchased locally, and this has commenced. DHCW will continue to drive value to the local supply chain in Wales, whilst maintaining high standards for goods and services. |
| 28 | 100% REGO-backed electricity will be procured by 2025, and 100% green gas by 2030. | DHCW procures 100% REGO-backed electricity for 3 buildings including for our largest workspace, which is also the biggest energy user. This equates to 60% of our electricity consumption being sourced from sustainable, renewable generation. This generated 114 tonnes of saving in 2020/21 and is an important procurement priority for DHCW. The Data Centres we use have confirmed that they purchase renewable electricity (and do not use natural gas for heating). DHCW is committed to moving to 100% REGO backed electricity by 2025 and 100% green gas by 2030. |
| 29 | NWSSP Procurement Services will embed NHS Wales’ decarbonisation ambitions in procurement procedures by mandating suppliers to decarbonise. | DHCW work closely with NWSSP and use Sustainable Procurement Code of Practice. DHCW uses the Welsh Government methodology for monitoring carbon emissions related to its procurement spend and this can be used to assess performance in decarbonisation of its purchases. |
| 30 | Sustainability will be embedded within strategic governance – NHS Wales - NWSSP Procurement Services will work across Wales to champion decarbonisation in the supply chain, and influence decarbonisation ambitions for buildings and transport | DHCW to continue to work closely with NWSSP and use Sustainable Procurement Code of Practice. DHCW uses the Welsh Government methodology for monitoring carbon emissions related to its procurement spend and this can be used to assess performance in decarbonisation of its purchases. |
| 31 | NWSSP Procurement Services will improve supply chain logistics and distribution to reduce the carbon emissions from associated transport. | DHCW to continue to work closely with NWSSP and use Sustainable Procurement Code of Practice. |
| 32 | NWSSP Procurement Services will actively develop and support procurement requirements to support implementation of the NHS Wales Decarbonisation Strategic Delivery Plan. | DHCW will ask NWSSP to work with them to assist in the Decarbonisation of our Procurement processes, as this is the most significant part of the DHCW carbon emission footprint. |

### 9.4.6 Estate Planning and Land Use

| No. | NHS Wales Initiative | DHCW Initiative |
| --- | --- | --- |
| 33 | All-Wales strategic estate planning will have carbon efficiency as a core principle – quantified carbon will be a key decision metric for planning new developments, rationalisation of the estate, and championing smart ways of working. | DHCW does not own any buildings. This provides a more agile and flexible capability in terms of the type and amount of workspace that we lease. Where practicable, we embed ourselves within workspaces that belong to other organisations, who would share our vision and ambition for decarbonised workspaces. DHCW strategic estate planning will have carbon efficiency as a core principle and will use this Decarbonisation Strategic Delivery Plan, the carbon accounting tools and its smarter working programme to deliver carbon efficiency across the Estate. |
| 34 | NWSSP and Welsh Government will advise Health Boards and Trusts on an appraisal approach for allocating land for uses such as renewable energy generation, greenhouse gas removal and afforestation – NHS Wales organisations will maintain green space and utilise land for decarbonisation, including collaborating with neighbouring landowners. | Initiative relates to NWSSP and Welsh Government land appraisal and is not applicable to DHCW. |
| 35 | Large-scale renewable energy generation opportunities with private wire connections to NHS Wales sites will be progressed where viable. | DHCW will be open to any opportunities for private wire connections to any of its sites. However, this may not be viable, given that DHCW does not own any of its properties. |
| 36 | Our approach to 21st-century healthcare will be central to the design of new hospital developments – redesigning the whole journey with care closer to home in a carbon-friendly primary care estate with a reduced need to visit hospitals. | Initiative is not applicable to DHCW, as this relates to the design of new hospitals. |

### 9.4.7 Approach to Healthcare – Smart Working

| No. | NHS Wales Initiative | DHCW Initiative |
| --- | --- | --- |
| 37 | Support the Welsh Government’s target for 30% of the Welsh workforce to work remotely, by continuing to facilitate flexible and smart working, developing the existing approach to remote working technology, and rationalising existing office space. | DHCW has New Ways of Working policies and procedures in place and provides remote working technology to all of our staff and will aim to exceed 30% of our workforce working remotely. Many of our staff and contractors are able to work effectively remotely. It is envisaged that remote working will be an integral part of our day-to-day activities and that there will have been a parallel decarbonisation of Wales’s electricity supply such that we are optimistic that our carbon emissions from electricity consumption in the office or the remote location will naturally reduce. Apart from its own staff, DHCW has a huge influencing role to enable increased remote working in other parts of NHS Wales. DHCW is committed to identifying opportunities for remote working and working with NHS Wales partners to implement supporting systems, as well as designing and maintaining such systems to ensure that they operate effectively. The Welsh Government target for remote working (30%) has already been exceeded in 2020/21. Whilst it is not envisaged that the levels of home working achieved during the pandemic will be maintained, DHCW does intend to; - maintain the capacity to achieve >90% remote working in a similar scenario to the current pandemic - maintain >30% remote working during normal years - play a lead role in facilitating remote working for other parts of NHS Wales - provide resources and incentives to staff to use less carbon intensive modes of transport when they do commute |
| 38 | Continue to utilise technology to increase the efficiency of engagements between staff and the public where suitable. | DHCW will continue providing technology services to primary and secondary care services enabling them to continue to utilise virtual services i.e. ‘Teams’ and ‘Attend Anywhere’, for online consultations. DHCW will be at the forefront of digital technology and is expecting to increase its workforce to respond to a demand for virtual services and associated data management. |

### 9.4.8 Approach to Healthcare – Education

| No. | NHS Wales Initiative | DHCW Initiative |
| --- | --- | --- |
| 39 | Health education will be used to champion decarbonisation across our service – we will encourage sustainable healthcare practice, waste efficiency, and low carbon staff and patient behaviour. | DHCW raise awareness of all of the above good practices on a regular basis through monthly Environmental Awareness communications, the Environmental SharePoint page etc. All DHCW employees are also required to undertake Environmental, Waste and Energy Training. DHCW formally review our environmental management status annually, using data to scrutinise our performance and inform future priorities, adjusting to take advantage of any opportunities or to correct any areas of weakness. |

### 9.4.9 Approach to Healthcare – Healthcare and Medicines

| No. | NHS Wales Initiative | DHCW Initiative |
| --- | --- | --- |
| 40 | Support the work of existing working groups such as the Welsh Environmental Anaesthetic Network to raise awareness of the carbon impact of medical gases and transition to a culture where gases with low global warming potentials are prioritised | Initiative not applicable to DHCW as it relates to the use of medical gases. |
| 41 | Explore methods of minimising gas wastage and technologies to capture expelled medical gases. | Initiative not applicable to DHCW as it relates to the use of medical gases. |
| 42 | Take a patient-centric approach to optimise inhaler use, focusing on a reduction in the overreliance of reliever inhalers where possible and emphasising the importance of inhaler-specific disposal and recycling. | Initiative not applicable to DHCW as it relates to the use of inhalers. |
| 43 | Transition the existing use and distribution of carbon-intensive and high global warming potential (GWP) inhalers to alternative lower GWP inhaler types where deemed suitable. | Initiative not applicable to DHCW as it relates to the use of inhalers. |

### 9.4.10 Approach to Healthcare – Waste

| No. | NHS Wales Initiative | DHCW Initiative |
| --- | --- | --- |
| 44 | Support the development of guidance by 2022 for best practice reduction of pharmaceutical waste. | Initiative not applicable to DHCW as it relates to reducing pharmaceutical waste. |
| 45 | Develop a 'plastics in healthcare' initiative to address waste in the delivery of health care – this will aim to tackle PPE, single use plastics, and packaging waste. | DHCW use PPE such as face coverings, gloves when attending patient facing healthcare settings. DHCW will participate and contribute to all strategies delivering single use plastics and packaging waste, without compromising patient or staff safety. DHCW will adopt all relevant guidance from NHS Wales. DHCW will adopt remote working strategies to minimise the need to enter clinical settings and use PPE. DHCW delivers as close to zero to landfill as possible. |
| 46 | Engage with pharmacists and prescribers to build upon and support existing efforts to encourage responsible disposal of inhalers through discussions with patients, information leaflets, posters and media. | Initiative not applicable to DHCW as it relates to the use of inhalers. |

# ROADMAP

## 10.1 NHS Wales approach

NHS Wales has set out a strategic roadmap for its NHS Wales Initiatives, summarising planned activity on each of the 46 initiatives out to 2030. DHCW has set out its own roadmap below. By following this roadmap, we are confident of achieving the NHS Wales 2025 and 2030 targets for our Operational Footprint (Roadmap Buildings and Transport elements).

•	2025 Target 16% reduction – predicted 21%.

•	2030 Target 34% reduction – predicted 35%.

The Roadmap to Procurement targets is less certain. NHS Wales has set out a strategic roadmap, which gives NWSSP the strategic role in leading all of the procurement strands of the NHS Wales Delivery Plan. DHCW’s role is a supporting one and the DHCW Roadmap for Procurement is indicative only, relying as it does on an NWSSP low-carbon procurement strategy that is to be developed. The NHS Wales carbon footprint for 2018/19 shows ICT-related procurement as a very small (<5%) component of the overall procurement footprint and centrally, NWSSP might rightly focus elsewhere, on the more sizeable components. Conversely, DHCW’s footprint is dominated by ICT-related procurement, and by definition DHCW are the subject-matter experts within NHS Wales. For these reasons, while working within NWSSP’s Delivery Plan framework, DHCW must provide leadership on emissions reduction in ICT procurement.

## 10.2 Roadmap Review and Revision

The roadmap below will be regularly reviewed, initially at the end of 2022 as by then NWSSP’s strategy should be available and improvements in footprint methodologies (particularly for procurement) may have revealed a need to change the path of some Roadmap actions. It is anticipated that the outlined actions shown below will be incorporated into DHCW’s detailed annual ISO14001 Objectives, which include a robust structure for defined targets, responsibilities, and intra-year timescales, along with a well-established process for routine review.

If regular review shows that the Roadmap is not delivering the forecast emission reductions, additional actions may be considered. Some could achieve significant reduction but come with significant change. For example;

- Moving to datacentres with a 100% renewables direct-wire PPA (Purchase Power Agreement) would enable all data centre emissions to be removed from the footprint under existing rules, leading to an additional 29% reduction on the forecast 2030 footprint. Availability of such datacentres within Wales by 2030 is not within DHCW’s control, although DHCW could engage with other Public Sector datacentre customers to encourage providers down this route.

- Reducing staff headcount back to around the 600 FTE level would reduce commuting and homeworking emissions, leading to an additional 5% reduction on the forecast 2030 footprint. This figure is provided for illustration; no view is given on DHCW’s continued ability to deliver its organisational goals with such a reduction. If anything, future demand for digital services may lead to a headcount increase, which put additional pressure on DHCW’s footprint aspirations.

## 10.3 DHCW Roadmap

|  | Buildings | Transport | Procurement | Approach to Healthcare |
| --- | --- | --- | --- | --- |
| 2021 | Action Plan and Building Priorities to be agreed to deliver a 1% year on year energy efficiency reduction. | 4 EV charging points to be installed. | Develop an understanding of NWSSP carbon accounting tool for Procurement of DHCW goods and services. | 96% of staff working remotely during the pandemic. |
| 2022 | Implement actions to improve carbon footprint methodologies (see Section 6). Liaise with all landlords with regards to the BMS capabilities, LED lighting coverage and REGO certification. Recommence roll-out of LED lighting. Improve building management to allow 1% year-on-year reductions in emissions related to natural gas consumption. Implement priority ‘TM44’ energy survey recommendations. Explore option for shared accommodation to enable notice to be given on small site. Datacentre carbon working group to work with providers and use Best Practice Guidance of the EU CofC on Data Centre Energy Efficiency for decision making regarding (e.g.); - Selection and Deployment of new IT Equipment - Deployment of New IT Services - Management of Existing IT Equipment and Services - Data Management - IT Reporting | Implement actions to improve carbon footprint methodologies (see Section 6). 2 EV vans to be trialled. Liaison with lease vehicle companies to understand opportunities. Liaise with landlords with regards to increasing the number of EV charging points. Staff travel survey to be undertaken. Developing Travel Plan and practical measures (cycle storage and showers, EV charging etc.) to (with the aid of national measures) reduce carbon intensity of commuting by 5% by 22/23. Working smarter to enable a 10% year-on-year reduction in business mileage (on 2019 baseline). | Implement actions to improve carbon footprint methodologies (see Section 6) including thorough review of spending to remove double-counting and wrongly allocated spending. Devise procurement methodology not wholly dependent on spend and emission factors. Work with NWSSP to develop a strategy for low-carbon ICT procurement, including (e.g.) building carbon reduction requirements into invitations to tender; developing (or adopting) low carbon standards for ICT equipment, as part of NWSSP’s Sustainable Procurement Code of Practice. Datacentre carbon working group to work with providers and use Best Practice Guidance of the EU CofC on Data Centre Energy Efficiency for monitoring of datacentre performance. | Implement actions to improve carbon footprint methodologies (see Section 6). Evaluate the best operational model for DHCW with regards to working remotely post pandemic & maintain a minimum 30% working remotely strategy. Promote home working energy efficiency measures to staff. |
| 2023 | Estate Rationalisation: 1 floor sub-letting at TGA Estate Rationalisation: option to vacate smaller location. Continue LED lighting roll-out. 1% y-o-y reductions in gas-related emissions. Use of datacentres with a PUE of 1.3 or better by 2023/24. | Review the EV opportunities for lease vehicles. Working smarter to enable a 10% year-on-year reduction in business mileage. | Roll out Sustainable Procurement Code of Practice as provided by NWSSP. | Maintain a minimum 30% working remotely strategy. DHCW will work with its ICT suppliers with regards to unnecessary waste packaging and single use plastic. |
| 2024 | Liaise with landlords to convert remaining buildings electricity tariff to REGO renewable. 1% y-o-y reductions in gas-related emissions. Estate Rationalisation: option to vacate smaller location. Complete LED lighting roll-out Upgrade/refurbishment of largest energy consuming office building. We will adopt cloud computing services using a cloud-first approach for both new and existing workloads. | Promote EV opportunities for staff within the lease car scheme. Significant drive for public and active travel and implement a plan to reduce the carbon intensity of staff commuting. Working smarter to enable a 10% year-on-year reduction in business mileage. Further develop Travel Plan and practical measures to (with the aid of national measures) reduce carbon intensity of commuting by 10% by 26/27. | Regular review and revision of low-carbon ICT strategy with NWSSP. | Maintain a minimum 30% working remotely strategy. Promote home working energy efficiency measures to staff. |
| 2025 | Estate Rationalisation: option to vacate smaller location. 1% y-o-y reductions in gas-related emissions 100% REGO electricity will have been procured. Use of datacentres with a PUE of 1.2 or better by 25/26. | DHCW will review the electric options for its remaining fleet vehicles and increase the proportion of electric vehicles in use. Working smarter to enable a 10% year-on-year reduction in business mileage. | NWSSP will have updated to market based emissions accounting and will engage with supply chains to support decarbonisation. Assist in this process for major ICT contracts. Engagement with key suppliers on decarbonisation. | Maintain a minimum 30% working remotely strategy. DHCW will continue to develop digital technology to support a smart communication approach between NHS sites and with the public at home. |
| 2026 | Estate Rationalisation: 2 floor sub-letting at TGA . 1% y-o-y reductions in gas-related emissions. | Strategy of Working smarter to ensure a 5% year on year business travel reduction. Working smarter to enable a 10% year-on-year reduction in business mileage. | Engagement with key suppliers on decarbonisation. | Maintain a minimum 30% working remotely strategy. Promote home working energy efficiency measures to staff. |
| 2027 | Investigate alternatives to natural gas heating. Use of datacentres with a PUE of - or better by 2027/28. 1% y-o-y reductions in gas-related emissions. | Working smarter to enable a 10% year-on-year reduction in business mileage. | Engagement with key suppliers on decarbonisation. | Maintain a minimum 30% working remotely strategy. |
| 2028 | Liaise with landlords to install non fossil fuel heating in TGA for completion by 2030. | All leased vehicles will be electric (or hybrid if rural network of EV charging points not yet fully operational). | Engagement with key suppliers on decarbonisation. | Maintain a minimum 30% working remotely strategy. Promote home working energy efficiency measures to staff. |
| 2029 | Estate Rationalisation: 3 floor sub-letting at TGA . | Working smarter to enable a 10% year-on-year reduction in business mileage. | Engagement with key suppliers on decarbonisation. | Maintain a minimum 30% working remotely strategy. |
| 2030 | Every building will have undergone an energy efficient upgrade – low carbon heating, renewable electricity purchased and most energy efficient building that is practicable. DHCW will have a smaller physical footprint through smarter working practices. | Continue to work smarter to enable a 10% year-on-year reduction in business mileage. All leased vehicles will be electric (fully EV, where rural network of EV charging points allows. | NHS Wales believes that significant parts of the supply chain will have progressed to net zero emissions. | Maintain a minimum 30% working remotely strategy. Promote home working energy efficiency measures to staff. |

# Conclusions

Digital Health and Care Wales has assessed its baseline carbon footprint for 2019/20. The gross carbon emissions for scopes 1, 2 and 3 were 19,858 T CO2e (net 19,652 T CO2e). This includes the emissions generated from remote working, as well as the use of third party Data Centres.

Procurement related emissions were the largest component (87%) of our carbon footprint, and the category with the most uncertainty. The plan to reduce procurement related emissions is being led by NWSSP through their own Delivery Plan.  However, with our digital expertise, we acknowledge that we have a major role to play in assisting NWSSP to identify realistic reduction pathways for procurement of IT Goods and Services. We will work with NWSSP in 2022 to scope out the way forward so that numeric reduction targets may be set for subsequent years.

Our Delivery Plan is focused on our Office Buildings and Data Centres, all Transport (business, fleet and staff commuting) and activities (i.e. non-procurement activities). Working remotely is also included as it demonstrated significant carbon reduction savings in 2020/21 and is a work model that DHCW can effectively adopt.

The Decarbonisation Pathway has been designed to achieve the NHS Wales 2025 and 2030 targets of 16% and 34% emissions reductions in the gross Operational emissions. DHCW has forecast its non-procurement ‘Operational’ emissions up to 2029/30 to predict the impact of key actions in our Delivery Plan.

Our modelling of predicted carbon reductions from this Plan gives a 21% reduction by 2025 and a 35% reduction by 2030 DHCW intends to review and report on its carbon footprint annually. This will then be the opportunity to assess performance against predicted carbon emissions. It is likely that individual years may vary up or below predictions but that the 2025 and 2030 targets are achievable by carrying out the proposed decarbonisation initiatives.

Immediate Decarbonisation Initiatives (2021-2025) have been identified and prioritised as follows:

| Priority | Initiative |
| --- | --- |
| 1 | With NWSSP, accelerate carbon accounting tools for procurement related carbon emissions and fast track DHCW procurement activities in the overall decarbonisation pathway, beginning in 2022. |
| 2 | Consolidate working remotely as a future operational model and embed in the strategic direction of DHCW. |
| 3 | Review the Estates Strategy to actively reduce the physical workspace. |
| 4 | Work closely with the Data Centres to optimise energy efficiency and its close monitoring. Migrate to Cloud computing services to enhanced energy savings. |
| 5 | Accelerate the energy reduction programmes at our office buildings, in particularly prioritising the installation of LED lights, upgrading air handling and BMS and ensuring smart metering is throughout the portfolio. Carry out early investigations into the feasibility of phasing our natural gas for heating purposes. |
| 6 | Undertake a Travel Survey in 2022 and continue liaison with lease vehicle providers to increase the availability of electric alternatives. |
| 7 | Support the use of electric vehicles through the installation of EV charging points across DHCW and for areas outside of our control, engage with our landlords to install additional EV charging points. |
| 8 | Create a Decarbonisation Team, with senior leadership, adopting an ‘urgency’ approach to the criticality of its remit and scope. |

DHCW is committed to playing its part in the decarbonisation of NHS Wales. The targets are challenging but achievable, they will require increased provision of resources, and pro-active micromanagement of all aspects of carbon accounting and improvement programmes.

# Glossary

Carbon footprint - a term for the carbon emissions from an organisation or individual. A carbon footprint will likely also include non-carbon greenhouse gases, such as methane or refrigerants, which also contribute to climate change.

CO2e - Carbon dioxide equivalent is a term for describing different greenhouse gases in a common unit. For any quantity and type of greenhouse gas, CO2e signifies the amount of CO2, which would have the equivalent global warming impact.

Emission Factor - a coefficient that allows conversion of activity data into GHG emissions. It is the average emission rate of a given source, relative to units of activity or process.

Greenhouse Gas Protocol (or GHG Protocol) - an international standard for reporting on emissions of greenhouse gases such as carbon dioxide.

Greenhouse gases (GHG) - gases that have been identified as contributing to climate change. The main definition of GHGs comes from the Kyoto Protocol, and includes carbon dioxide and methane as the main sources of warming.

Power Utilisation Efficiency (PUE) – a measure of data centre energy efficiency, which divides the amount of power coming into a data centre by the amount of power used to run data centre information technology equipment (cooling systems, UPSs, etc.).

REGO - Renewable Energy Guarantee of Origin certificates; certificates which show that electricity (or gas) has been generated from a low-carbon source.

Scope 1 Emissions - Direct emissions from combustion of gas and other fuels.

Scope 2 Emissions - Emissions resulting from the generation of electricity and other energy purchased.

Scope 3 Emissions - Emissions made by third parties in connection with operational activities.

WEEE - Waste Electrical and Electronic Equipment.

Well-to-Tank - also known as upstream or indirect emissions, is an emissions factor, which accounts for all the GHG emissions released into the atmosphere from the production, processing and delivery of a fuel or energy.

# References

Avgerinou, M., Bertoldi, P., & Castellazzi, L. (2017). Trends in Data Centre Energy Consumption under the European Code of Conduct for Data Centre Energy Efficiency. Energies.

Carbon Trust. (2020). NHS Wales carbon footprint 2018 to 2019. Retrieved 11 01, 2021, from https://gov.wales/sites/default/files/publications/2020-09/nhswales-carbon-footprint-2018-19.pdf

Carbon Trust. (2021). NHS Wales Decarbonisation Strategic Delivery Plan. Retrieved 11 8, 2021, from https://gov.wales/nhs-wales-decarbonisation-strategic-delivery-plan

Climate Change Committee. (2021). Independent Assessment of UK Climate Risk: Advice to Government. Retrieved 11 22, 2021, from https://www.theccc.org.uk/wp-content/uploads/2021/07/Independent-Assessment-of-UK-Climate-Risk-Advice-to-Govt-for-CCRA3-CCC.pdf

Dept for Business, Energy & Industrial Strategy. (2020). Greenhouse gas reporting: conversion factors 2019. Retrieved 11 15, 2021, from https://www.gov.uk/government/publications/greenhouse-gas-reporting-conversion-factors-2019

EcoAct. (2020). Homeworking Emissions Whitepaper. Retrieved 11 16, 2021, from https://info.eco-act.com/en/homeworking-emissions-whitepaper-2020

Environment Agency. (2008). Greenhouse gas emissions of water supply and demand management options. Retrieved 11 12, 2021, from https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/291728/scho0708bofv-e-e.pdf

GHG Protocol. (2004). Corporate Accounting and Reporting Standard (Revised Edition). Retrieved 11 08, 2021, from https://ghgprotocol.org/sites/default/files/standards/ghg-protocol-revised.pdf

HM Government. (2019). Environmental Reporting Guidelines: Including streamlined energy and carbon reporting guidance. Retrieved 11 15, 2021, from https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/850130/Env-reporting-guidance_inc_SECR_31March.pdf

IPCC. (2021). The Physical Sciences Basis, Sixth Assessment Report. Intergovernmental Panel on Cllimate Change.

National Grid ESO. (2020). Future Energy Scenarios. Retrieved 11 18, 2021, from https://www.nationalgrideso.com/document/173821/download

RAC Foundation. (2013). The Car and the Commute: The Journey to Work in England and Wales. Retrieved 11 16, 2021, from https://www.racfoundation.org/assets/rac_foundation/content/downloadables/car-and-the-commute-web-version.pdf

Welsh Government. (2017). Welsh public sector to be carbon neutral by 2030. Retrieved 11 08, 2021, from https://gov.wales/welsh-public-sector-be-carbon-neutral-2030

Welsh Government. (2019). Prosperity for All: A Low Carbon Wales. Retrieved November 26, 2021, from https://gov.wales/sites/default/files/publications/2019-06/low-carbon-delivery-plan_1.pdf

Welsh Government. (2021). All Wales Plan 2021-25: Working Together to Reach Net Zero. Retrieved 11 22, 2021, from https://gov.wales/working-together-reach-net-zero-all-wales-plan

Welsh Government. (2021). Net zero carbon status by 2030: A route map for decarbonisation across the Welsh public sector. Retrieved 11 22, 2021, from https://gov.wales/sites/default/files/publications/2021-07/a-route-map-for-decarbonisation-across-the-welsh-public-sector.pdf

Welsh Government. (2021). Welsh Public Sector Net Zero Carbon Reporting Guide. Retrieved 11 12, 2021, from https://gov.wales/public-sector-net-zero-reporting-guide